Commonwealth Blue Charter

Request for proposals for a Reviewer-Expert on the Blue Economy:

Blue Economy Rapid Readiness Assessment

TERMS OF REFERENCE

Overview

The Commonwealth Secretariat is seeking to engage a qualified consultant with expertise in the field of sustainable blue economy to provide third-party review and constructive criticism of two pilot Blue Economy Rapid Readiness Assessments in selected Commonwealth countries (Antigua & Barbuda and Trinidad & Tobago). This part-time, short-term consultancy will include providing unbiased expert guidance (written and remotely at meetings) and review of project materials, working with the Commonwealth Secretariat and its delivery partners. The consultancy is open to individuals and to consortia of more than one person.

Background, objectives and purpose

The Commonwealth is a voluntary association of 56 independent and equal sovereign states, home to 2.4 billion people. The Commonwealth Secretariat is an independent organisation working with the 56 member countries, assisting them to together promote prosperity, democracy and peace, amplify the voice of small states, and protect the environment.

The Commonwealth Secretariat’s Trade, Ocean and Natural Resources Directorate assists its member countries to sustainably manage their natural resources, in the ocean and on land, for the benefit of present and future generations. The Secretariat provides technical assistance supporting member countries in the development of policies, laws, fiscal regimes and strengthening national institutions.

The Commonwealth Blue Charter is an agreement by Commonwealth countries to actively cooperate in addressing the myriad of ocean-related challenges and commitments that they face. In April 2018, the Commonwealth Blue Charter was adopted by member countries to guide cooperative action on ocean issues. Commonwealth Blue Charter Action Groups are member-driven, led by Commonwealth Blue Charter ‘Champion’ countries.

The Commonwealth Secretariat, in partnership with the UN Environment Programme (UNEP) and other partners, is identifying two Commonwealth countries to assess their readiness to embark on the transition to a Sustainable Blue Economy (SBE). A Sustainable Blue Economy is one that seeks to promote economic growth and improve livelihoods across a range of maritime sectors while ensuring the sustainable use of marine resources. Implementing an SBE requires moving away from business as usual and integrating ocean sustainability throughout decision-making.

As part of UNEP’s work to promote and enable a Sustainable Blue Economy (SBE), it has developed a prototype version of a Sustainable Blue Economy Transition Framework (SBE-TF), to support countries and stakeholders develop SBE policy pathways and implementation strategies at local, national and regional level. In order to test and refine the SBE-TF, UNEP has enlisted the Commonwealth Secretariat to pilot the SBE-TF in selected countries and regions through the Rapid Readiness Assessment (RRA) process.

The primary objective of the RRA is to support participating countries in answering: “what desired national impacts will justify transitioning to a SBE?” and “what will need to be readied in order to implement the TF approach?” Through a combination of workshops, information gathering and analysis, the RRA will support countries to:

- collectively identify and map out the initial steps necessary to improve their SBE;

- assess their readiness for taking forward the TF approach; and

- identify priority enabling actions and resources needed.

This RRA project will run from August 2022 to November 2022. The project will be coordinated through the Commonwealth Blue Charter programme.

As a pioneering approach to the complex challenges facing maritime nations, UNEP’s SBE Transition Framework is a work in progress, and undertaking the RRA process in Antigua and Barbuda, and Trinidad and Tobago will inform its’ future development. To support the learning process and maximise beneficial outcomes for the countries involved, the Commonwealth Secretariat seeks through this consultancy to secure additional and independent expert support.

The consultant will work with the Commonwealth Secretariat, its delivery partners and two in-country Coordinators to provide third-party analysis and review of the RRA process, including the key stages of stakeholder engagement, information gathering, analysis and reporting. This will include attending meetings and events with the project team as well as in-country stakeholders, review of reports and providing advice and observations on the RRA as it proceeds.

By the end of this project (22 November 2022), government representatives will better understand the information, options, and next steps in making the transition to a sustainable blue economy. The consultant should have expertise in evaluating and advising on blue economy development, preferably in developing and/or middle-income countries, and preferably with experience working in the Caribbean or with other island nations.

Expected Deliverables and Location

The consultant will provide review and analysis support of two pilot blue economy rapid readiness assessments working with in-country Coordinators, Commonwealth Secretariat and the delivery partners.

Expected deliverables include (but not limited to) the following:

- Assist in reviewing and refining project materials, including the methodology and stakeholder survey;

- Provide helpful feedback on the RRA process;

- Provide an independent and detailed review of the draft assessment reports and results, including constructive criticism, additional text, options and insights;

- Participate in virtual meetings / workshops;

- Assist in editing / reviewing the analytical reports of the two countries

- Draft a brief internal final report outlining activities, time spent, outcomes, and reflections on lessons learned.

The work may be conducted from any location. The appointed Contractor should provide their own computer equipment, computer applications and internet connection.

Duration and Timeframe

Final deliverables will be due by 22 November 2022. Suggested milestones are listed in the table below but can be revised after a timeline is agreed upon.

| Deliverable | Final Due Date |
| --- | --- |
| Draft timeline and workplan | 12 September 2022 |
| Review and provide feedback on the RRA methodology | October 2022 |
| Provide an independent and detailed review of two draft RRA reports and results | November 2022 |
| Final report | 22 November 2022 |

Project Management and Reporting

The project will be coordinated by the Commonwealth Blue Charter Section of the Trade, Ocean and Natural Resources Directorate of the Secretariat. The successful Contractor will be expected to work in close consultation with the Commonwealth Blue Charter Team.

Estimated Budget

The maximum budget payable under this contract is £4,000 (including VAT, and any other fees). Payment will be made upon satisfactory completion of work signed off by the Commonwealth Secretariat and within 30 days upon submission of the invoice.

There may be some travel involved for which there will be a separate budget allocated.

Qualifications & Competencies

The preferred Contractor or consultancy firm should hold the profile below, which should be outlined in a concise cover letter and CV:

- University degree required in a field relevant to this work; e.g. marine science, environmental management,  environmental statistics, blue economy etc.

- Demonstrable experience of more than 5 years working in or with government department(s) relevant to sustainable blue economy - preferably a range of countries and experiences, including island nations;

- Demonstrated analytical, research, and writing skills;

- Interpersonal skills and cultural sensitivity;

- Ability to meet tight deadlines;

- Excellent communication skills;

- A strong commitment to collaborative approaches.

Application Process

Please apply for this contract by submitting a CV and a concise cover letter (1-2 pages) to bluecharter@commonwealth.int by 31 August 2022.

The cover letter should include the candidate’s / team’s relevant expertise and experience along with the bid amount. Bids must include all relevant fees and taxes, which in total cannot exceed the maximum amount (£4,000).

Evaluation will be based on both competency and cost. Where submissions are similar in quality, preference will be given to Contractors that are Commonwealth citizens or entities registered in a Commonwealth country.