Commonwealth Blue Charter

Request for proposals for In-country Coordinators:

Blue Economy Rapid Readiness Assessment

TERMS OF REFERENCE

Overview

The Commonwealth Secretariat is seeking to engage qualified in-country coordinators in Antigua & Barbuda and Trinidad & Tobago (2 positions) to assist in delivering a Blue Economy Rapid Readiness Assessment. This short-term consultancy will include identifying and coordinating with government and stakeholders in the selected country, supporting planning and delivery of workshops, liaising with the Commonwealth Secretariat and its delivery partners to execute the project plan, and ensuring timely completion of rapid assessment consultations with stakeholders. The consultancy is open to individuals and to consortiums of more than one person.

Background, objectives and purpose

The Commonwealth is a voluntary association of 56 independent and equal sovereign states, home to 2.4 billion people. The Commonwealth Secretariat is an independent organisation working with the 56 member countries, assisting them to together promote prosperity, democracy and peace, amplify the voice of small states, and protect the environment.

The Commonwealth Secretariat’s Trade, Ocean and Natural Resources Directorate assists its member countries to sustainably manage their natural resources, in the ocean and on land, for the benefit of present and future generations. The Secretariat provides technical assistance supporting member countries in the development of policies, laws, fiscal regimes and strengthening national institutions.

The Commonwealth Blue Charter is an agreement by Commonwealth countries to actively cooperate in addressing the myriad of ocean-related challenges and commitments that they face. In April 2018, the Commonwealth Blue Charter was adopted by member countries to guide cooperative action on ocean issues. Commonwealth Blue Charter Action Groups are member-driven, led by Commonwealth Blue Charter ‘Champion’ countries.

The Commonwealth Secretariat, in partnership with the UN Environment Programme (UNEP) and other partners, is identifying two Commonwealth countries to assess their readiness to embark on the transition to a Sustainable Blue Economy (SBE). A Sustainable Blue Economy is one that seeks to promote economic growth and improve livelihoods across a range of maritime sectors while ensuring the sustainable use of marine resources. Implementing an SBE requires moving away from business as usual and integrating ocean sustainability throughout decision-making.

As part of UNEP’s work to promote and enable a Sustainable Blue Economy (SBE), it has developed a prototype version of a Sustainable Blue Economy Transition Framework (SBE-TF), to support countries and stakeholders develop SBE policy pathways and implementation strategies at local, national and regional level. In order to test and refine the SBE-TF, UNEP is piloting the SBE-TF in selected countries and regions through the Rapid Readiness Assessment (RRA) process.

The primary objective of the RRA is to support participating countries in answering: “what desired national impacts will justify transitioning to a SBE?” and “what will need to be readied in order to implement the TF approach?” Through a combination of workshops, information gathering and analysis, the RRA will support countries to:

- collectively identify and map out the initial steps necessary to improve their SBE;

- assess their readiness for taking forward the TF approach; and

- identify priority enabling actions and resources needed.

This RRA project will run from August 2022 to November 2022. The project will be coordinated through the Commonwealth Blue Charter programme. With support from the Secretariat, the in-country coordinators will work with Government representatives and stakeholders in participating countries to deliver the RRA. The in-country coordinator should have good ties and networks within the selected countries and understand the political dynamics in relation to the ocean sector / blue economy.

The Commonwealth Secretariat is seeking an in-country coordinator for Antigua & Barbuda and for Trinidad & Tobago (one for each country) to identify and coordinate government stakeholders in the selected country, liaise with the Commonwealth Secretariat to execute the project plan, and ensure timely completion of consultation with relevant stakeholders. The consultancy is open to individuals and to consortiums of more than one person, so long as they remain within the total budget allocation.

Expected Deliverables and Location

The contractor will support the Commonwealth Secretariat throughout the process of completing the RRA in the respective countries. The rapid assessment consultations will need to be completed by 31 October 2022, followed by submission of a final (internal) report 22 November.

Expected deliverables include (but not limited) to the following:

- Assist in identifying government officials and stakeholders to join a virtual workshop to introduce the methodology;

- Coordinate with the country to review and provide feedback on the methodology following the workshop;

- Assist with delivery of the rapid assessment:

  - identify government, NGO, and private sector stakeholders

  - undertake desk-based gathering of information relevant to the RRA such as sustainable development policy documents, blue economy-relevant reports, etc.

  - organise and undertake meetings with key individuals to complete the RRA questionnaire, with support from project partners (based in the UK)

  - distribute (online and in-person) surveys to stakeholders, and

  - follow up to ensure their timely completion;

- Convene and join calls to support the consultation process, as required;

- Assist in the convening of a second virtual (or possibly in-person) meeting / workshop to discuss the RRA process with government and stakeholders;

- Write a brief final report outlining activities, time spent, outcomes, feedback on the RRA process, reflections on challenges, any lessons learned and/or suggestions.

The contractor needs to be based in the respective countries (Antigua & Barbuda and Trinidad & Tobago). The appointed Contractor should provide their own computer equipment, computer applications and internet connection.

Duration and Timeframe

Final deliverables will be due by 22 November 2022. Suggested milestones are listed in the table below but can be revised after a timeline is agreed upon.

| Deliverable | Final Due Date |
| --- | --- |
| Draft timeline and workplan | 29 August 2022 |
| Identify and make contact with stakeholders to be engaged in the RRA process | 12 September 2022 |
| Assist in planning and delivery of introductory workshop / webinar | September/October 2022 |
| Plan and undertake RRA survey with key stakeholders | 31 September 2022 |
| Follow up to ensure timely completion of surveys and feedback | October 2022 |
| Assist in organisation and delivery of second workshop | November 2022 |
| Final report | 22 November 2022 |

Project Management and Reporting

The project will be coordinated by the Commonwealth Blue Charter Section of the Trade, Ocean and Natural Resources Directorate of the Secretariat. The successful Contractor will be expected to work in close consultation with the Commonwealth Blue Charter Team.

Estimated Budget

The maximum budget payable under this contract is £6000 per position (including VAT, and any other fees). (Note: The Secretariat is hiring for 2 x in-country coordinator positions, one for each country). Payment will be made upon satisfactory completion of work signed off by the Commonwealth Secretariat and within 30 days upon submission of the invoice.

Qualifications & Competencies

The preferred Contractor or consultancy firm should hold the profile below, which should be outlined in a concise cover letter and CV:

- University degree required in a field relevant to this contract, such as, environmental management, marine, ocean sciences, government / stakeholder relations, etc.

- Demonstrable experience of more than 4 years in working with government departments and stakeholders; ideally, relevant to marine or coastal planning and/or climate change in the respective country;

- Excellent interpersonal skills;

- Excellent communication skills to build collaborative relationships and supportive engagement with stakeholders;

- Skilled at managing competing priorities and meeting tight deadlines;

- Solid writing abilities;

- A strong commitment to partnership and collaborative approaches.

Application Process

Please apply for this contract by submitting a CV and a concise cover letter (1-2 pages) to bluecharter@commonwealth.int by 22 August 2022. The email subject line should clearly indicate which country the applicant will be based in.

The cover letter should include the candidate’s / team’s relevant expertise and experience along with the bid amount. Bids must include all relevant fees and taxes, which in total cannot exceed the maximum amount (£6000 per position).

Evaluation will be based on both competency and cost. Where submissions are similar in quality, preference will be given to Contractors that are Commonwealth citizens or entities registered in a Commonwealth country.