COMMONWEALTH SECRETARIAT

MARLBOROUGH HOUSE, PALL MALL, LONDON SW1Y 5HX

IN STRICT COMMERCIAL CONFIDENCE

Request for Quotations (RFQ)

For the Provision of Technical Assistance and Consultancy Services to support the Government of The Gambia to Produce a New National Sports Policy

July 2023

| Secretariat Reference Number: | GSC0005-2023 |
| --- | --- |
| Return Date: | Return Date – 12.00 Noon BST on 11/08/23 |
| Estimated Contract Award: | September 2023 |

Contents

1.	Introduction	3

2.	Purpose	3

3.	Instructions to Bidders	3

4.	Evaluation Weightings	3

5.	Quote Timeline	4

6.	Information for Bidders	4

7.	Specification of Requirements (SoR)/ Terms of reference (ToR)	5

Part 1 – Bidder Details (for information)	12

Part 2 - Suitability Assessment Questions (pass/fail)	13

Part 3 – Technical Questionnaire	18

Part 4 – Pricing	21

Annex 1 -     Secretariat’s Technical Assistance Consultants: Corporate Fee Band Table

# Introduction

The Commonwealth Secretariat (The Secretariat) is an international organisation established by Agreed Memorandum, which is given privileges and immunities under the domestic law of the United Kingdom by the Commonwealth Secretariat Act 1966 (as amended by the International Organisations Act 2005). Under this legislation, the Secretariat is not subject to UK jurisdiction and enforcement.

This status has an impact on some of our standard terms and conditions. In particular, we draw your attention to our dispute resolution clause, which refers disputes to the exclusive jurisdiction of the Commonwealth Secretariat Arbitration Tribunal (CSAT). The 8 members of the Tribunal are selected by the Board of Governors and come from Commonwealth member countries. Information about CSAT, including its governing statute and procedure are available on its website at http://thecommonwealth.org/tribunal.

The Secretariat implements decisions agreed by 56 Heads of Government and Ministers through advocacy, consensus–building, information sharing, analysis, technical assistance, capacity-building, and advice on policy development.

# Purpose

The purpose of this request for a quote (RFQ) is to find and appoint a suitable consultant for the provision of Technical Assistance to the Commonwealth Secretariat to support the Government of The Gambia to produce a new National Sports Policy. The appointed consultant shall be awarded a contract that will be effective for up to six(6) months.

See Terms of Reference in Section 7 for details on the services required.

# Instructions to Bidders

This is a one stage RFQ process with a written submission to this RFQ followed by bidder clarifications, if required. Bidders will be scored following the first stage and if required bidders may be asked to attend a clarification of their Quote meeting.

Bidders must submit all documents as set out in Part1 – Part 5 ‘Quote’ no later than the return date of 12.00 Noon BST on 11/08/23. The quote documents are to be returned to the following email address: c.brooks@commonwealth.int.

Following all stages of the Quote process, the quote received that is deemed as offering best overall value to the Commonwealth Secretariat, shall be awarded the contract based on the notified evaluation weightings:

# Evaluation Weightings

Quality 70%

See Part 3 of the Technical Questionnaire for a more detailed breakdown of the appoprtionment of this weighting.

Price 30%

The lowest price bid shall be awarded the full points, all other bids shall be awarded a percentage from the benchmark. E.g. (lowest price/other bid)*weighting = Score.  Further information on the Quality and Technical weightings can be found in Part 3 – Technical Questionnaire.

# Quote Timeline

Please note, that the following timeline is an estimate and may change at short notice.

| Activity | Date |
| --- | --- |
| Request for quote (RFQ) issued | 21/07/23 |
| Clarification questions to be submitted by bidders by | 04/08/23 |
| Secretariat’s response to (anonymised) clarification questions will be circulated to all in writing by | 08/08/23 |
| Quotes submission closing date | 12.00 BST on 11/08/23 |
| Contract Start Date | September 2023 |

# Information for Bidders

- Unless indicated otherwise, all prices should be quoted in Pounds Sterling. Prices quoted for Technical Assistance Consultancy should include all travel, per diem and taxes and should be submitted on an all inclusive fixed basis, providing a breakdown of day rates per named Consultant mapped against the Secretariat’s TAP Consultants: Corporate Fee Band Table (annexed to this RFQ)

- The bidder must ensure that they have all the information required for the preparation of the Quote submission and that they are satisfied about the correct interpretation of terminology used in this documentation. The bidder must also ensure that they are fully conversant with the nature and extent of the obligations should the Quote be accepted.

- Quotes are to be valid for a minimum of 30 days from the closing date for the submission of the Quotes.

- The Commonwealth Secretariat reserves the right to cancel the RFQ at any time during the process and not to award a contract as a result of this procurement.

- Bidders shall bear all costs in completing a quotation submission.

- Bidders shall not disclose details of the RFQ to third parties without prior agreement from an authorised officer of the Commonwealth Scretariat.

- All clarification queries must be submitted by 17.00 BST on 04/08/23 and only to c.brooks@commonwealth.int.

- Bidders are required to submit transparent pricing with no hidden costs or charges.

- The Secretariat will carry out an evaluation of the quotes using the weighted criteria method as described. Following the evaluation stage(s) the Secretariat will select a preferred bidder which will be taken forward to contract award. The Secretariat reserves the right to appoint a reserve preferred bidder which the Secretariat could then take forward to contract award if any contract negotiations with the preferred bidder are unsuccessful.

By taking part in this request for quotes all bidders commit to the following:

- Bidders confirm that by submitting a quote they agree to abide by the Secretariat’s Code of  Ethics and relevant Corporate policies as published from time to time on the following web page:

Corporate Policies | Commonwealth (thecommonwealth.org)

- Bidders certify that they have not canvassed or solicited any officer or employee of the Secretariat in connection with this Quote submission and that no person employed or acting on behalf of the bidder has done any such act.

- The CSAT shall have exclusive jurisdiction to settle any dispute or claim that arises out of or in connection with this Procurement (including non-contractual disputes or claims).

# Terms of reference (ToR)

Contract Title: The Development of a New Sports Policy for The Gambia 2023-2032

Location: The Gambia / Remote

Contract duration: 40+ person days (September 2023 to February  2024)

Contract amount: GBP £29,950 including VAT if applicable and travel expenses.

Closing date: 	11/08/23

Background

The Commonwealth is a voluntary association of 56 independent sovereign states, which cooperate in the common interests of their citizens, to further international understanding, development and democracy. The Commonwealth’s membership has great diversity of economic strength, geography and ethnicity, combined with a common heritage of values, language, institutions and democratic traditions. The Commonwealth Secretariat is the principal intergovernmental body of the Commonwealth, responsible for progressing and achieving the shared goals of the association’s member governments in advancing democracy, development and respect for diversity.

Through the Commonwealth Secretariat Strategic Plan 2021-2025 and following the 10th Commonwealth Sports Ministers Meeting (10CSMM) held in July 2022, the Secretariat has been mandated to assist member countries to intentionally use sport to provide innovative policy and program-based solutions to contribute to national health, education, and social inclusion outcomes.  Specifically, the Secretariat will support member countries to develop, implement and measure the impact of policies and strategies aimed at maximizing the contribution of sport to national development objectives and the Sustainable Development Goals (SDGs). To do this the Commonwealth Secretariat delivers targeted technical assistance projects, produces guidelines, toolkits and other technical resources for member countries, and, organises related capacity, training, events and high-level meetings.

Development of a new National Sports Policy for The Gambia

The Government of The Gambia is committed to undertaking an evaluation of the National Sports Policy 2010-2019 and the development of a new National Sports Policy which will provide the Ministry of Youth and Sports with a clear programme of action that can be delivered over the next 10 years. This project is the main priority of the Ministry for 2022/23 and it is a primary objective that the new National Sports Policy will be built upon the strengths of the previous policy as well as lessons learned.  For this new policy, the Secretariat is recommending the creation of a Monitoring and Evaluation Framework alongside the development of the new strategy so that the implementation of the new Policy has an accountability system from the point that it is adopted.

The Government is mindful of the fact that for sports to assume its pride of place as a crosscutting activity within the Development Agenda, a consultative, collaborative and coordinated approach is required in order to elicit the desired outcomes. The broad-based consultations leading to the development of this sport policy would ensure that all stakeholders take ownership of responsibility for and participation in the effective implementation of the sports policy, thereby ensuring sustainable delivery across all the thematic areas of engagement in a more effective and inclusive manner. The overarching vision of the Gambia’s sport policy, for the next decade, is to maintain and sustain this momentum and to galvanize the sporting fraternity to a higher level of leading edge characterized by sporting engagement and excellence across all sporting disciplines.

Sport is generally and widely accepted as a veritable instrument for social cohesion, and personal growth and development. As a unifying and potent force, sport has the capacity to galvanize societies as well as motivate athletes, both amateur and professionals to maximize their potentials and to be the very best that they can be. Hence the Government is very conscious of the solidarity effects of sports and has requested Technical Assistance from the Commonwealth Secretariat.  It is expected that this work will consult widely with different stakeholders including government ministries and departments, national sporting associations, community-based sports entities, municipalities, athletics and officials as well as media practitioners.

The sport policy will endeavor to realize the Vision of Government as provided for in the National Development Plan on sports and to incorporate the basic principles and guidelines that underpin sport development.

The government in collaboration with technical assistance support from the Commonwealth Secretariat will establish a National Sports Policy Taskforce consisting of key sports and non-sport agencies and organizations which will guide the development of the new policy and associated frameworks.

In summary, the Commonwealth Secretariat has committed to provide technical assistance to support the evaluation of the previous National Sports Policy and the development of the new policy on the basis of a request from the Ministry of Youth and Sport received through an Expression of Interest dated 19/09/22. A visit to The Gambia was also undertaken to hold a high-level meeting to discuss the type of services that could be provided.  The outcome of this meeting was to develop this Terms of Reference to recruit a suitable consultant or local expert to undertake the work in partnership with the Ministry of Youth and Sport and the Commonwealth Secretariat.

Purpose and key deliverables of the Assignment

The primary purpose of the assignment is to provide technical assistance to the Ministry of Youth and Sport to develop a new National Sports Policy which maximises the contribution of sport to deliver national strategic objectives and the SDGs. To do this, it is a priority of the Ministry to review and evaluate the successful impact of the previous policy, building on strengths and successes but also ensuring lessons are learned.  The new National Sports Policy will need to be developed through a collaborative and inclusive consultation process securing effective engagement and buy-in from a range of stakeholders. The final policy should articulate links between it and The Gambia National Strategic Plan and, where appropriate, African Union sports policies and plans.  It is also of critical importance to ensure that alongside the creation of the new policy, a robust Monitoring and Evaluation Framework is produced.  It is expected that the policy and framework are produced to meet the bespoke needs of stakeholders in The Gambia but that best practice examples from other Commonwealth member countries are used as benchmarks.  This delivery of this assignment should also, where possible, assist in building the capacity of key officials to update and implement the new policy.

A summary of key deliverables of the assignment include:

- A Project Inception Report detailing the methodology for the overall assignment

- An Evaluation Report for the previous National Sports Policy 2010-2019

- A baseline Needs Assessment Report for the new policy based on a desktop review and quantitative and qualitative assessment using a range of methods (focus groups, interviews and surveys)

- Workshop series to inform the development of the new policy

- A draft National Sports Policy and Monitoring and Evaluation (M&E) Framework and Implementation Plan for review and further consultation

- Final drafting of the National Sports Policy and M&E Framework

Full Scope of services and deliverables

To fulfil this assignment, the consultant will be required to deliver the following outputs:

- Project Inception Report

  - Set out the methodology and work programme for the project, following the Project Inception Meeting, to include:

    - Detailed methodology for each stage and output of the project

    - Detailed consultation and engagement plan – what, why, where, when, how etc

    - A clear and realistic work plan with planned activities mapped against a weekly timeline including regular update meetings with the Taskforce and Com Sec team;

    - An information requirements list including documents, contact details and any other resources required from the Taskforce/ Com Sec team

    - Roles and responsibilities plan split between the main contributors – the Consultant, Com Sec and, where relevant, our partner organisations.

    - A basic risk assessment and mitigation plan

- Evaluation Report for the National Sports Policy 2010-2019 adopting a theory-based approach using/adapting any existing theory of change or developing a new theory of change, as a basis for the evaluation and for the creation of the new Sports Policy.  Key tasks to include:

  - Create an agreed set of evaluation questions utilising the OECD/DAC criteria of; relevance, coherence/alignment, effectiveness, efficiency, impact and sustainability

  - Undertake interviews with an agreed set of key stakeholders using the evaluation questions

  - Identify key strengths, weaknesses, challenges, and key opportunities for development/ improvement based on the evaluation

  - Recommendations for the new Sports Policy and its implementation

- Baseline Needs Assessment Report presenting the findings from both quantitative and qualitative assessment methods including:

  - Results of desk-research and analysis of national and regional policy alignment opportunities as well as pathways for the policy to help The Gambia progress its work to deliver the SDGs

  - Assessment of capacity to implement a robust M&E system involving data collection and regular progress reporting on an annual or biannual basis

  - Analysis of data, both quantitative and qualitative, collected from desk research and stakeholder consultation, surveys and focus groups to be defined in the Project Inception Report

  - Recommendations to inform the development of the new National Sports Policy, including key resource implications, governance structures and additional capacity building requirements

- Draft National Sport Policy White Paper for review and further consultation

  - Plan and deliver a minimum of two workshop sessions with key stakeholders to review and validate the findings from deliverables 2 and 3 and begin identifying priority areas for the new National Sports Policy

  - Drafting of initial policy white paper based on the outcomes of the workshop sessions

  - Administration of feedback and collation of inputs, feedback and amendments

- Publication of a Results Framework and Draft Monitoring and Evaluation Plan to support policy implementation and sustainability

  - Development of a Draft Results Framework and Monitoring and Evaluation Plan in collaboration with the Taskforce and stakeholders to support policy administration and impact measurement

  - Analysis and mapping of existing national results frameworks and performance indicators for sport with the Sport and SDG Model Indicators produced by the Commonwealth Secretariat.

  - Proposed structure, format and deliverables for the framework and M&E system including the administration of such a framework

  - Development and publication of a long term implementation plan to support the Ministry and sector stakeholders to deliver the Policy

  - Final Draft National Results Framework and M&E system on the contribution of sport to national development

  - Recommendations to operationalise the M&E system, including key resource implications and additional capacity building requirements based on baseline needs assessment and the delivery of one familiarisation workshop

- Final Draft of the National Sports Policy

  - Following consultation on the first draft, make necessary amendments to produce a Final Draft of the National Sports Policy in collaboration with the Taskforce and Com Sec team

Approach and Implementation Arrangements

The project will be overseen by the Sport for Development and Peace Project Manager at the Commonwealth Secretariat. Engagement with the Government of The Gambia will be under the direction of the Ministry of Youth and Sport and supported by a bespoke Taskforce set up by the Ministry. The assignment will be delivered through a collaborative approach, the consultant(s) is expected to liaise with and work as part of team that will include the Taskforce and relevant other ministries, Commonwealth Secretariat staff and partner organisations/ collaborators.

The total fee quoted in proposals should include all travel and subsistence requirements and any tax payable by the consultant.

Application Process

To apply, interested parties should submit a Fee Proposal in accordance with the requirements in the Request for Quotations (RFQ) by the stated deadline containing the following:

- Overview of proposed approach to the assignment, including:

  - Methodology for each deliverable

  - Proposed scope of each service/activity

  - Total time and personnel commitment for the assignment

  - Total budget for the assignment

- Example(s) of previous work that demonstrate capability to complete the assignment;

- In addition to the above:

- For individuals: a detailed CV outlining their educational qualifications, professional engagements, and a list of other, relevant work undertaken; and

For organisations and institutions:  a prospectus outlining their relevant experience and achievements together with the CVs of experts who would work on the assignment.

Conflicts of interest

The consultant shall establish and maintain appropriate business standards, procedures and controls including those necessary to avoid any real or apparent impropriety or to prevent any action or conditions which could result in conflict with the Secretariat’s best interests.

If either Party becomes aware of any actual or possible conflict between the interests of the Secretariat and the Consultant, it shall notify the other Party as soon as reasonably possible and the Parties shall meet to discuss the Conflict and shall: (i) use all reasonable endeavours to find ways to eliminate or minimise the risk of the Conflict; and (ii) take such steps as may be agreed to remove or avoid the cause of the Conflict.

8 List of Deliverables/Payment schedule:

Timeline for deliverables and estimated milestone payments

| Milestone date | Deliverable | % of fee |
| --- | --- | --- |
| 29/09/23 | - Project Inception Report | 20% |
| 27/10/23 | - Evaluation Report for the National Sports Policy 2010-2019 | 20% |
| 31/12/23 | - Baseline Needs Assessment Report | 20% |
| 31/01/24 | - Draft National Sport Policy White Paper, Results Framework, Monitoring and Evaluation Plan | 30% |
| 16/02/24 | - Final Draft of the National Sports Policy | 10% |

9 Contract Management

The successful consultant will report to the Secretariat’s Contract Manager Caroline Brooks, Sport and SDGs Project Manager – c.brooks@commonwealth.int.

10 Monitoring/ Reporting requirements

Specific arrangements for contract management will be as follows:

Weekly progress reports provided by the Consultant.

Monthly progress meetings (or more frequently as necessary) led and co-ordinated by the Consultant.

11 Methodology

The Consultant must provide a detailed methodology as per the Terms of Reference.

12 Skills and experience required

Qualification and Skill Requirements

Applicants as individuals or as part of a company should possess:

- A post-graduate qualification in a relevant discipline.

- Expert knowledge in the use of sport as a development tool, in particular in the development or application of national policy.

- General expertise designing policy across social and economic policy domains.

- Expertise in measurement and evaluation of national policy.

- A sound understanding of the Sustainable Development Goals and implications for the development, measurement and evaluation of public policy.

- Success in authoring publications or official reports for national governments, intergovernmental meetings and/or policy orientated fora.

- Cross cultural competency, with experience working in Commonwealth developing countries, particularly in Africa, is highly desirable.

Applicants should be able to demonstrate in their fee proposals:

- A track record of success supporting national policy development and producing related reports, policy documents and outputs for governments and/or intergovernmental stakeholders.

- Proven ability to design implementable policies and strategies for public authorities across social and economic policy domains.

- Proven ability to develop and support the implementation of Results Framework and M&E systems

- A strong understanding of how to successfully structure sport sectors for the effective and efficient delivery of sports policies.

- Capability to plan, design and deliver national-level workshops on public policy development, implementation and monitoring and evaluation.

- Proven ability to undertake needs assessment consultation and analysis pertaining to national policy development.

- Proven ability to think laterally and apply innovative thought to policy, design, and to develop practical policy recommendations.

- High level written and interpersonal communication skills.

This consultancy assignment is expected to require a Consultant at Band B or C of the Secretariat’s Technical Assistance Consultants: Corporate Fee Band Table (see Annex).

13 Evaluation criteria

The Technical Questionnaire Quotes will be assessed based on the evaluation criteria set forth in this document (see skills and experience required and the weightings apportioned to quality/price above in this Terms of reference/RFQ).

Part 1 Bidder’s details is for information only.

Part 2 - Suitability Assessment Questions -will be assessed on a Pass/Fail basis

14 Payments

Payments will be made in line with the schedule of deliverables outlined above and upon successful completion of the milestones, upon receipt of the Secretariat’s written approval of all agreed deliverables and upon submission of a compliant invoice and any other supporting documents as may be required by the Secretariat from time to time. All invoices to be sent to contract manager c.brooks@commonwealth.int.

Quote Submission Documents for the provision of Technical Assistance and Consultancy Services to support the Government of The Gambia to produce a new National Sports Policy

Note - Bidders must complete and return all Quote submission documents below:

Part 1 – Bidder Details

Part 2 – Suitability Assessment Questions

Part 3 – Technical Questionnaire

Part 4 – Pricing

Part 1 – Bidder Details (for information)

Please provide details relating to your registered offices, legal status and date of incorporation.

| Individual/ Company and/or Trading Name |  |  |  |  | Company/Sole Trader Registration Number |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Company Address |  |  |  |  | Date of incorporation |  |  |  |  |
| Post Code |  |  |  |  |  |  |  |  |  |
| Contact Name |  |  |  |  | Job Title |  |  |  |  |
| Telephone |  |  |  |  | Email |  |  |  |  |
| In the event of utilising a third party, on your behalf for any part of the services, please provide the full details of the secondary consultant/supplier: |  |  |  |  |  |  |  |  |  |
| Company Name |  |  |  |  | Duration of working relationship, |  |  |  |  |
| Company Address |  |  |  |  | Reason for use |  |  |  |  |
| Post Code |  |  |  |  |  |  |  |  |  |
| In line with the Secretariat’s Procurement Code of Ethics, the Secretariat works towards encouraging SMEs to apply for relevant tenders and is committed to monitoring the environmental awareness of our consultants, suppliers and partners with a view (where relevant to the subject matter of the contract) to only doing business with ISO 14001 Environmental Management or ISO 50001 Energy Management accredited organisations. |  |  |  |  |  |  |  |  |  |
| Is the Consultant classified as a Micro or Small Medium Enterprise (SME)?; Yes/No. Is the Consultant an ISO14001 or ISO 50001 (Energy Management) accredited organisation?; Yes/No. UK VAT Declaration For UK Registered consultants Is the bidder registered for Value Added Tax (VAT)? [Y/N] If Yes, please include VAT registration number [insert] and provide a copy of your VAT registration certificate as part of your response. Annual Turnover check: In line with the Secretariat’s Procurement Code of Ethics, the Secretariat expects for its consultant/suppliers to have a turn over that is, as a minimum, twice the value of the contract they are applying for. Please state the following: |
|  | Annual |  | Previous Year |  |  |  |  | Year 2 |  |
|  | Turnover: |  | £ |  |  |  |  | £ |  |
| Please note, the successful bidder (if a company and not an Individual) may also be checked for their Equifax Financial Credit Score. Should the bidder (if a company) fail the commercial credit score check, the Secretariat will be entitled to commence negotiations with the second preferred bidder subject to that bidder (if a Company) having passed the Equifax Credit Score and so forth. Please provide the contact details of two reference clients. References need to be for similar type projects. The referees will not be contacted until the final stage of the Quote process. Please provide references from similar international organisations or public sector bodies or equivalent if possible. |  |  |  |  |  |  |  |  |  |
|  |  | Reference 1 |  |  |  | Reference 2 |  |  |  |
| Company Name |  |  |  |  |  |  |  |  |  |
| Company Address |  |  |  |  |  |  |  |  |  |
| Post Code |  |  |  |  |  |  |  |  |  |
| Referees name |  |  |  |  |  |  |  |  |  |
| Referee Telephone |  |  |  |  |  |  |  |  |  |
| Referee Email |  |  |  |  |  |  |  |  |  |

Part 2 - Suitability Assessment Questions (pass/fail)

Grounds for Exclusion

You will be excluded from the Quote process if there is evidence of convictions relating to specific criminal offences including, but not limited to, bribery, corruption, conspiracy, terrorism, fraud and money laundering, or if you have been the subject of a binding legal decision which found a breach of legal obligations to pay tax or social security obligations.

- Within the past five years, have you or your organisation (or any member of your proposed consortium, if applicable)- if you are trading as a company - Directors or Partner or any other person who has powers of representation, decision or control been convicted of any of the following offences? Individual Consultants – please complete the table to the best of your knowledge.

| Please Mark ‘X’ In the Relevant Box | Yes | No |
| --- | --- | --- |
| - Conspiracy as defined by the legislative or judicial bodies in your jurisdiction. | s | x |
| - Corruption as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - Bribery as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - The offence of cheating the Revenue as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - The offence of conspiracy to defraud as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - Fraud as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - Theft as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - Fraudulent trading as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - Fraudulent evasion as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - Destroying, defacing or concealing of documents or procuring the execution of a valuable security as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - The possession of articles for use in frauds as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - Any offence considered to be Counter Terrorism as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - Money laundering as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - Any Sexual Offences as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - Drug trafficking as defined by the legislative or judicial bodies in your jurisdiction. |  |  |

- Within the past three years, please indicate if any of the following situations have applied, or currently apply, to you (if an Individual Consultant) or your organisation.

| Please Mark ‘X’ In the Relevant Box | Yes | No |
| --- | --- | --- |
| - You/your organisation is bankrupt or is the subject of insolvency or winding-up proceedings, where your assets are being administered by a liquidator or by the court, where it is in an arrangement with creditors, where its business activities are suspended or it is in any analogous situation arising from a similar procedure under the laws and regulations of any State; |  |  |
| - You/your organisation is guilty of grave professional misconduct, which renders its integrity questionable; |  |  |
| - You/your organisation has entered into agreements with other economic operators aimed at distorting competition; |  |  |
| - the prior involvement of you/your organisation in the preparation of the procurement procedure has resulted in a distortion of competition; |  |  |
| - you/your organisation has shown significant or persistent deficiencies in the performance of a substantive requirement under a prior contract with a contracting entity, or a prior concession contract, which led to early termination of that prior contract, damages or other comparable sanctions. |  |  |

- Employment and Human Rights

For organisations working outside of the UK please refer to equivalent legislation in the country that you are located. Please delete ‘Yes’ / ‘No’ as applicable.

| (a) | In the last three years, has any finding of unlawful discrimination been made against you/your organisation by an Employment Tribunal, an Employment Appeal Tribunal or any other court (or in comparable proceedings in any jurisdiction other than the UK)? | Yes/No |
| --- | --- | --- |
| (b) | In the last three years, have you or has your organisation had a complaint upheld following an investigation by the Equality and Human Rights Commission or its predecessors (or a comparable body in any jurisdiction other than the UK), on grounds or alleged unlawful discrimination? If you have answered “yes” to one or both of the questions, please provide, as a separate Appendix, a summary of the nature of the investigation and an explanation of the outcome of the investigation to date. If the investigation upheld the complaint against your organisation, please use the Appendix to explain what action (if any) you have taken to prevent unlawful discrimination from reoccurring. You may be excluded if you are unable to demonstrate to The Secretariat’s satisfaction that appropriate remedial action has been taken to prevent similar unlawful discrimination reoccurring. | Yes/No |
| (c) | If you use sub-contractors, do you have processes in place to check whether any of the above circumstances apply to these other organisations? | Yes/No/ NA |

- Environmental Legislation

For organisations working outside of the UK please refer to equivalent legislation in the country that you are located. Please delete ‘Yes’ / ‘No’ as applicable.

| (a) | Have you or your organisation been convicted of breaching environmental legislation, or had any notice served upon it, in the last three years by any environmental regulator or authority (including local authority)? If your answer to this question is “Yes”, please provide details in a separate Appendix of the conviction or notice and details of any remedial action or changes you have made as a result of conviction or notices served. The Secretariat will not select bidders that have been prosecuted or served notice under environmental legislation in the last 3 years, unless The Commonwealth is satisfied that appropriate remedial action has been taken to prevent future occurrences/breaches. | Yes/No |
| --- | --- | --- |
| (b) | If you use sub-contractors, do you have processes in place to check whether any of these organisations have been convicted or had a notice served upon them for infringement of environmental legislation? | Yes/No/ NA |

- Health and Safety legislation

For individuals/organisations working outside of the UK please refer to equivalent legislation in the country that you are registered in and/or located. Please delete ‘Yes’ / ‘No’ as applicable.

| (a) | Please self-certify that your organisation has a Health and Safety Policy that complies with current legislative requirements. | Yes/No/NA (individual consultant) |
| --- | --- | --- |
| (b) | Has your organisation or any of its Directors or Executive Officers been in receipt of enforcement/remedial orders in relation to the Health and Safety Executive (or equivalent body) in the last 3 years? If your answer to this question was “Yes”, please provide details in a separate Appendix of any enforcement/remedial orders served and give details of any remedial action or changes to procedures you have made as a result. The Secretariat will exclude bidder(s) that have been in receipt of enforcement/remedial action orders unless the bidder(s) can demonstrate to The Secretariat’s satisfaction that appropriate remedial action has been taken to prevent future occurrences or breaches. | Yes/No/NA (individual consultant) |
| (c) | If you use sub-contractors, do you have processes in place to check whether any of the above circumstances apply to these other organisations? | Yes/No/ NA (individual consultant) |

- Insurance requirements (for information)

Does the Consultant (whether an Individual or Company) have insurances (as may be necessary or relevant by the subject matter of the contract specified in the Terms of Reference in this RFQ), currently in place, for the business activities they are proposing to carry out?

If Yes, please state the type of insurance and level of insurance held:

| Area | Does the Consultant/supplier have insurances in place? | Level of cover expected | Level of cover currently held |
| --- | --- | --- | --- |
| e.g. Public liability | Yes/No/NA | £10m |  |
| e.g. Employer’s liability | Yes/No/NA | £5m |  |
| e.g. Professional Indemnity | Yes/No/NA | £1m |  |
| e.g. Data Protection Liability | Yes/No/NA | £3m (or £10m where complex and sensitive data processing is involved) |  |

Please note that the Individual Consultant will not be excluded from the tender process if the answer is ‘No’. However, it is industry best practice for consultants to ensure they have suitable insurances in place for the work they are proposing to undertake.

Please note that the insurance cover detailed above should be in place before activities commence in pursuance of the services required and will not be considered as part of the costs under the contract between the Secretariat and the selected consultant.

- Terms and Conditions/Code of Ethics/Corporate Policies

Please delete ‘Yes’ / ‘No’ as applicable.

| (a) | Please confirm that you (if an Individual Consultant)/your organisation agrees to the Commonwealth Secretariat’s: 1. Secretariat’s standard terms and conditions for below £30,000 total contract value can be found at: Terms and Conditions ¦ Commonwealth (thecommonwealth.org) 2. Secretariat’s Code of Ethics at: Microsoft Word - Annex15 Code of Ethics - [updated January 2022].docx (production-new-commonwealth-files.s3.eu-west-2.amazonaws.com) and 3. Secretariat’s Corporate policies applicable to Consultant/suppliers and as published from time to time on the following web page: Corporate Policies ¦ Commonwealth (thecommonwealth.org) ………………………………………………………………………………………………………………….. If you do not agree to abide by the above, please state reasons and/or changes requested as part of your bid: | Yes/No |
| --- | --- | --- |

- Legal comments table

By submitting a response, the bidder is agreeing to be bound by the terms of this RFQ and the Contract save as in relation to those areas of the Contract specifically highlighted below.  As such, if the terms & conditions of the Commonwealth Secretariat Terms and Conditions | Commonwealth (thecommonwealth.org) renders proposals in the bidder’s response unworkable, the bidder must submit full details of the unworkable/unacceptable provisions within the relevant Standard Terms and Conditions (Consultancy) by completing the Legal Comments Table below.

| Clause/Paragraph /Schedule | Summary of Issue | Suggested Revisions |
| --- | --- | --- |

Part 3 – Technical Questionnaire

The following scoring mechanism will be used to score each question in this section:

| Using a 0 – 5 scoring system: |  |
| --- | --- |
| 0 | Unacceptable Response – No information provided or response does not address the requirement. |
| 1 | Poor response – The response contains material omissions and / or is supported by limited evidence / examples. Concerns that the organisation does not have the potential to deliver / that they have failed to meet a reasonable standard. |
| 2 | Fair response – There is adequate detail / supporting examples giving a reasonable level of confidence in the Tenderer’s experience and ability. The Tenderer appears to have the potential to deliver as required / has met a reasonable standard and there are only minor concerns about the Tenderer’s experience |
| 3 | Good Response – The level of detail / supporting examples gives a high level of confidence in the Tenderer’s experience and ability. The Tenderer clearly has the potential to deliver and / or has clearly met an acceptable standard. |
| 4 | Excellent Response – A comprehensive well evidenced submission, clearly demonstrating expertise and knowledge incorporating some value-added benefits attributes & other points of innovation. The bid is deemed to offer little risk and fully captures the understanding of the steps involved to deliver aspects of the service which can be related to the question posed, giving a high level of confidence in the Tenderer’s experience and ability. |
| 5 | Exceptional Response – A comprehensive and exceptionally evidenced submission that substantially exceeds the expectations of the requirement and offers significant additional benefits. Submission clearly demonstrates exceptional expertise and knowledge incorporating value added benefits/ & other points of innovation. The bid is deemed to offer well identified risks and a mitigation of these put forward and fully captures the understanding of the steps involved to deliver all the aspects of the service and is directly relatable to the question posed, giving an exceptionally high level of confidence in the Tenderer’s experience and ability. |

- The technical questions below are worth 70% of the total score. The individual question weightings as a % of 70% are set out in the weighting column.

- The following formula will be applied for each question:

  - Points Scored ÷ Points Available × % weighting

  - The scores for each of the questions will be added to give a total Technical/Quality Score

- Unanswered questions or sections that are left blank shall be awarded a 0.

Please answer all questions in the spaces provided. Please do not attach documents or appendices.

| Question No. | Question | Weighting |
| --- | --- | --- |
| 1 | Please demonstrate your understanding of the requirements of the Terms of Reference by highlighting the key issues, challenges and opportunities presented by the commission. | 15% |
| Insert your answer here |  |  |
| 2 | Please outline in detail your methodology for delivering the commission, directly referencing the scope of services and key deliverables and ensuring that the key issues, challenges and opportunities identified in question 1 are addressed through the approach you will undertake. Additional evaluation criteria including relevance, clarity and creativity of your approach will also be assessed. | 20% |
| Insert your answer here |  |  |
| 3 | Please outline in detail, an overview of your experience in undertaking similar assignments and be specific with the examples you reference to demonstrate: - Evidence of a strong track record of success supporting national policy development and producing related reports, policy documents and outputs for governments and/or intergovernmental stakeholders - Proven ability to undertake consultation and analysis to design implementable policies and strategies for public authorities across social and economic policy domains - Capability to design and support the implementation of Results Frameworks and M&E systems - Proven ability to think laterally and apply innovative thought to policy design and implementation methods and governance structures | 35% |
| Insert your answer here |  |  |

Part 4 – Pricing

Transparent pricing must be submitted with no hidden costs. Pricing and cost must be broken down to the different deliverables in the Terms of Reference and clearly identify any other costs assosicated with travel or other expenses.  The total budget available must include all travel expenses.

Please complete the Pricing Schedule and submit as a separate document. Please refer to Instructions to bidders which states that unless indicated otherwise, all prices should be quoted in Pounds Sterling.

Consultants are expected (within their financial proposal) to provide a full breakdown of the number of experts/number of days (total and per expert) needed to complete the assignment.

| Consultant’s Name/Role/Band – refer to Annex 1 Technical Assistance Consultants: Corporate Fee Band Table Experts name/role |  | Day Rate (including all taxes) | No of Days | Total (including all taxes) GBP |
| --- | --- | --- | --- | --- |
| Total |  |  |  |  |

Payments will be made upon successful completion of the milestones described in the terms of reference, upon receipt of the Secretariat’s written approval of all agreed deliverables and upon submission of a compliant invoice. If there is a VAT element - for UK VAT registered consultants only – this must be itemised in the total quote received/agreed by the Secretariat and the consultant must submit a UK VAT registration certificate to the Secretariat when invoicing. All invoices will be sent to contract manager – c.brooks@commonwealth.int.

Annex 1 – Secretariat’s Technical Assistance Consultants: Corporate Fee Band Table

The consultancy fee rate range associated with a particular level of assignment may be based on the following:

- Knowledge, qualifications, experience, and skills required.

- Level of work in terms of responsibilities and complexity of the assignment.

- Degree of specialization required by the assignment.

| Band | Per Day (GBP) | Comments and Guidelines |
| --- | --- | --- |
| A* | 700+ | - Extensive achievement in their specialist field, in which they are nationally or internationally renowned. Extensive experience of leading or directing major, complex and business-critical projects, bringing genuine strategic insight, understanding the range of services to be delivered. In depth knowledge of the international sector/specialist field and of current policy and political issues affecting it. - Contributions to the accomplishment of a crucial programme or service or functional area of a broad scope, involving high complexity and impact. - Providing functional leadership and expert advice. - Preparing intricate and complex technical papers to working groups. - Undertaking the drafting of reports or proposals for projects of a large scale or a broad scope. - Large-scale programmatic and operational activities involving large commitments of staff and funds. - Rare specialization - Industry equivalent level: Partner/Managing Director |
| B | 500-699 | - Substantial experience in their specialist field and operating multiple major consultancy assignments achieving specific revenue and income objectives to agreed outcomes. - Within this category the person is expected to have significant, proven, industry recognised experience. - Expected to develop new approaches, techniques, or policies and/or design guidelines, standard operating procedures. - Providing technical support; leading group dynamics; and undertaking report drafting or project-wide proposals. - Industry equivalent level: Principal/Senior Consultant |
| C | 350 - 499 | - Demonstrable experience and relevant exposure in a range of projects in a specialist field. - Evidence of client facing experience and relationship management. - Support for planning and monitoring budgets and services to wider consultancy projects; and experience of proposal preparation. - Industry equivalent level: Consultant |
| D | 300-349 | - Specialized degree or training and - Several years of relevant experience - Industry equivalent level: Junior Consultant |
| E | £100 - £299 | - This level is established for the engagement of support services not available in the Secretariat related to projects or technical tasks of a narrow scope for which limited technical skills or experience are required. - Industry equivalent level: Project Support |

*Rates above Band A must include appropriate justification in respect of the tasks involved, complexity of the assignment, number of workdays involved, duration/period and specific task deliverables and must, internally within the Secretariat, be referred to the DSG, ASG or Senior Director for review and approval ahead of any contract being awarded.

Microsoft Word - Annex15 Code of Ethics - [updated January 2022].docx (production-new-commonwealth-files.s3.eu-west-2.amazonaws.com)

Microsoft Word - Annex15 Code of Ethics - [updated January 2022].docx (production-new-commonwealth-files.s3.eu-west-2.amazonaws.com)