COMMONWEALTH SECRETARIAT

MARLBOROUGH HOUSE, PALL MALL, LONDON SW1Y 5HX

IN STRICT COMMERCIAL CONFIDENCE

Request for Quotations (RFQ) for Consultancy for requirements between £5,001 and below £30,000 (including travel, per diem and all taxes) over life of contract

For the provision of Analytical study to develop a roadmap for trade related regulatory coherence (conventional and digital) in selected Indo-Pacific countries

Ocotober 2024

| Secretariat Reference Number: | CCA RFQ LCC Q0503-10 |
| --- | --- |
| Return Date: | Return Date – 5pm GMT on 22/11/2024 |
| Estimated Contract Award: | November 2024 |

Contents

1.	Introduction	3

2.	Purpose	3

3.	Instructions to Bidders	3

4.	Evaluation Weightings	3

5.	Quote Timeline	4

6.	Information for Bidders	4

7.	Terms of reference	5

Part 1 – Bidder Details	8

Part 2 - Suitability Assessment Questions	9

Part 3 – Technical Questionnaire	13

Part 4 – Pricing	14

5. Pricing	15

Annex 1 -     Secretariat’s Technical Assistance Consultants: Corporate Fee Band Table 	      16

# Introduction

The Commonwealth Secretariat (The Secretariat) is an international organisation established by Agreed Memorandum, which is given privileges and immunities under the domestic law of the United Kingdom by the Commonwealth Secretariat Act 1966 (as amended by the International Organisations Act 2005). Under this legislation, the Secretariat is not subject to UK jurisdiction and enforcement.

This status has an impact on some of our standard terms and conditions. In particular, we draw your attention to our dispute resolution clause, which refers disputes to the exclusive jurisdiction of the Commonwealth Secretariat Arbitration Tribunal (CSAT). The 8 members of the Tribunal are selected by the Board of Governors and come from Commonwealth member countries. Information about CSAT, including its governing statute and procedure are available on its website at http://thecommonwealth.org/tribunal.

The Secretariat implements decisions agreed by 56 Heads of Government and Ministers through advocacy, consensus–building, information sharing, analysis, technical assistance, capacity-building, and advice on policy development.

# Purpose

The purpose of this request for a quote (RFQ) is to find and appoint a suitable consultant for the provision of Analytical study to develop a roadmap for trade related regulatory coherence (conventional and digital) in selected Indo-Pacific countries to the Commonwealth Secretariat. The appointed consultant shall be awarded a contract that will be effective for up to three (3) months.

See Terms of Reference in Section 7 for details on the services required.

# Instructions to Bidders

This is a one stage RFQ process with a written submission to this RFQ followed by bidder clarifications, if required. Bidders will be scored following the first stage and if required bidders may be asked to attend a clarification of their Quote meeting.

Bidders must submit all documents as set out in Part1 – Part 5 ‘Quote’ no later than the return date of: 5pm GMT on 22 November 2024. The quote documents are to be returned to the following email address: connectivity@commonwealth.int

Following all stages of the Quote process, the quote received that is deemed as offering best overall value to the Commonwealth Secretariat, shall be awarded the contract based on the notified evaluation weightings:

# Evaluation Weightings

Quality 70%

Price 30%

The lowest price bid shall be awarded the full points, all other bids shall be awarded a percentage from the benchmark. E.g. (lowest price/other bid)*weighting = Score.

# Quote Timeline

Please note, that the following timeline is an estimate and may change at short notice.

| Activity | Date |
| --- | --- |
| Request for quote (RFQ) issued | 22/10/2024 |
| Clarification questions to be submitted by bidders by | 18/11/2024 |
| Secretariat’s response to (anonymised) clarification questions will be circulated to all in writing by | 19/11/2024 |
| Quotes submission closing date | 5pm GMT/ 22-11-2024 |
| Contract Start Date | December 2024 |

# Information for Bidders

- Unless indicated otherwise, all prices should be quoted in Pounds Sterling. Prices quoted for Technical Assistance Consultancy should include all travel, per diem and taxes and should be submitted on an all inclusive fixed basis, providing a breakdown of day rates per named Consultant mapped against the Secretariat’s TAP Consultants: Corporate Fee Band Table (annexed to this RFQ)

- The bidder must ensure that they have all the information required for the preparation of the Quote submission and that they are satisfied about the correct interpretation of terminology used in this documentation. The bidder must also ensure that they are fully conversant with the nature and extent of the obligations should the Quote be accepted.

- Quotes are to be valid for a minimum of 30 days from the closing date for the submission of the Quotes.

- The Commonwealth Secretariat reserves the right to cancel the RFQ at any time during the process and not to award a contract as a result of this procurement.

- Bidders shall bear all costs in completing a quotation submission.

- Bidders shall not disclose details of the RFQ to third parties without prior agreement from an authorised officer of the Commonwealth Scretariat.

- All clarification queries must be submitted by 5pm GMT 22/11/2024 and only to connectivity@commonwealth.int

- Bidders are required to submit transparent pricing with no hidden costs or charges.

- The Secretariat will carry out an evaluation of the quotes using the weighted criteria method as described. Following the evaluation stage(s) the Secretariat will select a preferred bidder which will be taken forward to contract award. The Secretariat reserves the right to appoint a reserve preferred bidder which the Secretariat could then take forward to contract award if any contract negotiations with the preferred bidder are unsuccessful.

By taking part in this request for quotes all bidders commit to the following:

- Bidders confirm that by submitting a quote they agree to abide by the Secretariat’s Code of  Ethics and relevant Corporate policies as published from time to time on the following web page:

https://thecommonwealth.org/corporate-policies

- Bidders certify that they have not canvassed or solicited any officer or employee of the Secretariat in connection with this Quote submission and that no person employed or acting on behalf of the bidder has done any such act.

- The CSAT shall have exclusive jurisdiction to settle any dispute or claim that arises out of or in connection with this Procurement (including non-contractual disputes or claims).

- Compliance with policies: The Secretariat has a zero-tolerance approach towards sexual exploitation, abuse and harassment. The bidder must familiarise itself with the Secretariat’s policies available at https://thecommonwealth.org/corporate-policies  Particularly with reference to the Anti- Bribery and the Safeguarding Policy, the bidder must understand the obligations imposed on Suppliers/Consultants and their personnel and sub-contractors including having robust procedures to detect and report any wrongdoing or concerns. Adherence to the Secretariat policies is mandatory and if awarded a contract, the Supplier/Consultant will be required to ensure continued compliance with the policies for the duration of the contract.

# Terms of reference (ToR)

Introduction

Trade, Oceans and Natural Resources Directorate (TONRD)

TONR is one of the three Directorates of the Commonwealth Secretariat. The Directorate brings together work in Trade Policy, Competitiveness, Connectivity Agenda for Trade and Investment, and Oceans and Natural Resources. TONRD is responsible for contributing to the delivery of the organisation’s strategic outcomes: (i) greater adherence to Commonwealth values and principles and advance good governance, through strengthened rule of law, democracy, peacebuilding, human rights, public institutions, and electoral processes enabled by value-based leadership; (ii) sustainable and inclusive economic and social development pertaining to trade, financial and debt management, oceans and natural resources management and, health and education systems; (iii) climate-resilient and low-carbon development to respond to climate and ocean emergencies, through intra-Commonwealth co-operation on sustainable ocean action and energy transition and increased mitigation and adaptation actions; and (iv) small and other vulnerable states’ needs and concerns will be addressed in global governance mechanisms and their resilience to shocks increased.

Commonwealth Connectivity Agenda

At the 2018 Commonwealth Heads of Government Meeting, the Commonwealth adopted the Declaration on the Commonwealth Connectivity Agenda for Trade and Investment (CCA). The CCA is a major new member-state led initiative to grow intra-Commonwealth trade and investment to US$2 trillion by 2030 and promote expanded investment to support global growth, create employment, and promote knowledge exchange among Commonwealth members. The CCA focusses on five clusters of work: physical connectivity reducing physical barriers to trade; digital connectivity enabling all members to take advantage of the opportunities presented by digital trade; regulatory connectivity reducing regulatory barriers to trade; business to business connectivity focussing on investment and public-private dialogue and supply-side connectivity encouraging the participation of all members in global value chains. Throughout these areas, inclusive and sustainable trade, addressing women’s economic empowerment and youth unemployment are being mainstreamed.

Regulatory Connectivity Cluster:

This assignment falls within the Regulatory Connectivity Cluster (RCC) which focuses on improving understanding of various regulatory regimes and advancing the ease of doing business through promoting good regulatory practice including regulatory cooperation among member countries. The objective is to reduce non-tariff barriers, improve services data collection, and mutual recognition to reduce regulatory barriers, address the capacity deficit and improve the regulatory environment for business, especially micro, small, and medium enterprises, and consumers.

Background of the assignment

The Indo-Pacific region has emerged as an important area for global trade, encompassing economies with diverse regulatory frameworks. This varying regulatory environments across conventional and digital sectors pose challenges to seamless trade. Regulatory coherence is vital for harmonizing standards, reducing barriers, and fostering greater economic integration. In this context, this study aims to develop a “roadmap for regulatory coherence” (both conventional and digital) in selected Indo-Pacific countries — (Australia, New Zealand, Samoa, Fiji, India, and Malaysia) — to enhance trade opportunities within the region.

Purpose/objectives of the assignment:

The primary objectives of this analytical study are; to:

-Develop a comprehensive roadmap for regulatory coherence in both conventional (physical goods, services) and digital sectors (e-commerce, data flows, digital services etc).

-Identify key regulatory barriers in selected countries and explore ways to harmonize regulations to enhance trade.

-Propose actionable recommendations for policy/regulatory reforms, capacity building, and regional collaboration to achieve regulatory coherence in the Indo-Pacific region.

Scope of Work and specific tasks

Under the direct supervision of the Advisor Regulatory framework and overall guidance of the Head of Commonwealth Connectivity Agenda, the selected consultant will:

I. Country-Specific Analysis:

- Conduct a detailed analysis of the regulatory frameworks for trade in Australia, New Zealand, Samoa, Fiji, India, and Malaysia.

- Survey the existing regulatory environment and identify commonalities and differences in the conventional and digital trade regime

- Identify regulatory barriers to trade in both conventional and digital sectors.

- Examine the alignment of these regulatory frameworks with international standards and best practices.

II. Digital Trade Regulations:

- Analyse digital trade regulatory and policy frameworks, focusing on e-commerce, cross-border data flows, digital services, digital trade facilitation and intellectual property rights etc.

- Identify discrepancies and gaps between digital regulations in the selected countries.

III. Conventional Trade and Regulations:

- Assess regulations related to market access, customs procedures, non-tariff barriers/measures, and trade facilitation.

- Highlight existing challenges in physical goods and services sectors that hinder trade integration

IV. Comparative Analysis and Best Practices:

- Compare regulatory practices across the selected countries and identify best practices in regulatory coherence.

- Draw lessons from successful international experiences in regulatory alignment and coherence.

V. Stakeholder Consultations:

- Engage with key stakeholders from the selected countries to gain insights on regulatory challenges and opportunities for reform.

- Conduct interviews and consultations with regulatory bodies, trade experts, and industry players to understand specific needs for regulatory harmonization.

VI. Roadmap Development:

- Develop a roadmap that outlines short, medium, and long-term actions to achieve regulatory coherence in conventional and digital sectors in selected countries.

- Propose specific policy recommendations, legislative reforms, and capacity-building initiatives for enhancing regulatory alignment across the selected Indo-Pacific countries.

VII. Regional Cooperation Mechanisms (covering both conventional and digital):

- Explore potential platforms and mechanisms for regional cooperation, including trade agreements, memorandums of understanding (MoUs), and other regulatory partnerships.

- Propose strategies for regional collaboration to support regulatory reforms and promote mutual recognition agreements (MRAs) under the support and umbrella of Commonwealth.

VIII. Validation and presentation

- Following the completion of the roadmaps and associated documents as explained above, present them in RCC meeting.

- Make a presentation of the study in the policy dialogue/roundtable (in person or virtual) of the member countries

Safeguarding:

The winning supplier will be actively taken through the Secretariat’s Safeguarding policy (amongst other Corporate Policies relevant for the contract)– by the Contract Manager - at inception meeting.

Conflicts of interest

## The consultant shall establish and maintain appropriate business standards, procedures and controls including those necessary to avoid any real or apparent impropriety or to prevent any action or conditions which could result in conflict with the Secretariat’s best interests.

## If either Party becomes aware of any actual or possible conflict between the interests of the Secretariat and the Consultant, it shall notify the other Party as soon as reasonably possible and the Parties shall meet to discuss the Conflict and shall: (i) use all reasonable endeavours to find ways to eliminate or minimise the risk of the Conflict; and (ii) take such steps as may be agreed to remove or avoid the cause of the Conflict.

8 List of Deliverables/Payment schedule:

The selected consultant will follow the following implementation and delivery framework to achieve the desired deliverables.

|  | Activities/deliverables | Time Frame |
| --- | --- | --- |
| 1 | Literature review and development of Issue paper (Based on I to IV) | Three weeks after the contract is awarded (Week 1, 2 & 3) |
| 2 | Discussion with Advisor RCC and Cluster lead | Within three days after receipt of issue paper (week 4) |
| 3 | Consultations with relevant stakeholders | Two weeks after the discussion at no 2 above (week 5 and 6) |
| 4 | Preparation of first draft roadmap and regional cooperation mechanisms | Two weeks after the consultations at no 3 (Week 7 &8) |
| 5 | Presentation at the RCC meeting | Meeting to be convened as appropriate |
| 6 | Presentation at the policy dialogue/round table | March 2025 |

Hard deliverables:

- Issue paper.

- Record note of meetings with stakeholders

- Draft and final roadmap and regional cooperation mechanisms

Soft deliverables:

- Discussion and presentation in RCC meeting and policy dialogue

Payment Milestones:

Maximum budget allowed for this consultancy is 15000 British pounds (all inclusive)

First payment: 75% after presentation of the guidelines in the RCC meeting and their subsequent finalization based on received comments.

Second and final payment: 25% after presentation at the virtual or in-person policy dialogue

9 Contract Management

The successful consultant will report to the Secretariat’s Contract Manager, Adviser- Regulatory Framework. Specific arrangements for contract management will be as follows:

- Regular updates provided via email the frequency of which will be decided by the parties

- Microsoft Teams calls/meetings as and when required or requested by either party

- All deliverables must be completed in accordance with the timelines set out in the table above.

10 Reporting requirements

Same as above

11 Methodology

Please ensure that your bid includes a detailed methodology outlining your approach to achieving the project objectives and delivering the required outcomes.

12 Skills and experience required

The successful consultant should have the following minimum qualifications and experience.

Education and Experience

- At least ten years’ experience working on developing regulatory frameworks, policy analysis, and impact assessments of regulatory frameworks is required.

- A master’s degree in economics, public policy, finance or related field is required (A Bachelor’s degree would be accepted in lieu of a Master’s degree with an additional two years relevant experience)

- Demonstrated experience in regulatory compliance, public administration, or related fields is desirable.

- Practical experience in conducting analysis of digital and conventional regulatory coherence is highly desirable. Experience in analysing complex data, assessing risks, and evaluating the effects of proposed regulations would be valued.

- Previous experience of working with International Organizations on similar assignments is desirable.

Language

- Excellent drafting skills in English

Knowledge, Skills and Abilities

- Proven skills for effective communication and collaboration are essential.

- Sound organisational and planning skills, including proven ability of meeting strict deadlines

- Reasonable flexibility to adapt to limited changes in the terms of reference

- Strong interpersonal and communication skills and ability to work constructively with internal and external stakeholders

This consultancy assignment is expected to require a Consultant at Band C of the Secretariat’s Technical Assistance Consultants: Corporate Fee Band Table (see Annex 1 Below).

13 Evaluation criteria

The Technical Questionnaire Quotes will be assessed based on the evaluation criteria set forth in this document (see skills and experience required and the weightings apportioned to quality/price above in this Terms of reference/RFQ).

Part 1 Bidder’s details is for information only.

Part 2 - Suitability Assessment Questions -will be assessed on a Pass/Fail basis

14 Payments

Payments will be made in line with the schedule of deliverables outlined above and upon successful completion of the milestones, upon receipt of the Secretariat’s written approval of all agreed deliverables and upon submission of a compliant invoice and any other supporting documents as may be required by the Secretariat from time to time. All invoices to be sent to contract manager Adviser, Regulatory Framework – Connectivity@commonwealth.int

Quote Submission Documents (ref CCA RFQ LCC Q0503-10)

Note - Bidders must complete and return all Quote submission documents below:

Part 1 – Bidder Details

Part 2 – Suitability Assessment Questions

Part 3 – Technical Questionnaire

Part 4 – Pricing

Part 1 – Bidder Details (for information)

Please provide details relating to your registered offices, legal status and date of incorporation.

| Individual/ Company and/or Trading Name |  |  |  |  | Company/Sole Trader Registration Number |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Company Address |  |  |  |  | Date of incorporation |  |  |  |  |
| Post Code |  |  |  |  |  |  |  |  |  |
| Contact Name |  |  |  |  | Job Title |  |  |  |  |
| Telephone |  |  |  |  | Email |  |  |  |  |
| In the event of utilising a third party, on your behalf for any part of the services, please provide the full details of the secondary consultant/supplier: |  |  |  |  |  |  |  |  |  |
| Company Name |  |  |  |  | Duration of working relationship, |  |  |  |  |
| Company Address |  |  |  |  | Reason for use |  |  |  |  |
| Post Code |  |  |  |  |  |  |  |  |  |
| In line with the Secretariat’s Procurement Code of Ethics, the Secretariat works towards encouraging SMEs to apply for relevant tenders and is committed to monitoring the environmental awareness of our consultants, suppliers and partners with a view (where relevant to the subject matter of the contract) to only doing business with ISO 14001 Environmental Management or ISO 50001 Energy Management accredited organisations. |  |  |  |  |  |  |  |  |  |
| Is the Consultant classified as a Micro or Small Medium Enterprise (SME)?; Yes/No. Is the Consultant an ISO14001 or ISO 50001 (Energy Management) accredited organisation?; Yes/No. UK VAT Declaration For UK Registered consultant: Is the bidder registered for Value Added Tax (VAT)? [Y/N] If Yes, please include VAT registration number [insert] and provide a copy of your VAT registration certificate as part of your response. Annual Turnover check: In line with the Secretariat’s Procurement Code of Ethics, the Secretariat expects for its consultant/suppliers to have a turn over that is, as a minimum, twice the value of the contract they are applying for. Please state the following: |
|  | Annual |  | Previous Year |  |  |  |  | Year 2 |  |
|  | Turnover: |  | £ |  |  |  |  | £ |  |
| Or |  |  |  |  |  |  |  |  |  |
| For individual consultants, please confirm that your annual turnover is twice the value of the Contract you are applying for: YES Please note, the successful bidder (if a company and not an Individual) may also be checked for their Equifax Financial Credit Score. Should the bidder (if a company) fail the commercial credit score check, the Secretariat will be entitled to commence negotiations with the second preferred bidder subject to that bidder (if a Company) having passed the Equifax Credit Score and so forth. Please provide the contact details of two reference clients. A minimum of two references will be collected from previous clients (excluding the Secretariat) from projects carried out in (max) last 18 months. Please provide references from similar international organisations or public sector bodies or equivalent if possible. One of the references should relate to the most recent contract you/your company has fulfilled. If possible, additionally, supply a list of potential references from which the Secretariat can select the referees they wish to contact. The referees will not be contacted until the final stage of the Quote process. |
|  |  | Reference 1 |  |  |  | Reference 2 |  |  |  |
| Company Name |  |  |  |  |  |  |  |  |  |
| Company Address |  |  |  |  |  |  |  |  |  |
| Post Code |  |  |  |  |  |  |  |  |  |
| Referees name |  |  |  |  |  |  |  |  |  |
| Referee Telephone |  |  |  |  |  |  |  |  |  |
| Referee Email |  |  |  |  |  |  |  |  |  |

Part 2 - Suitability Assessment Questions (pass/fail)

Grounds for Exclusion

You will be excluded from the Quote process if there is evidence of convictions relating to specific criminal offences including, but not limited to, bribery, corruption, conspiracy, terrorism, fraud and money laundering, or if you have been the subject of a binding legal decision which found a breach of legal obligations to pay tax or social security obligations.

- Within the past five years, have you or your organisation (or any member of your proposed consortium, if applicable)- if you are trading as a company - Directors or Partner or any other person who has powers of representation, decision or control been convicted of any of the following offences? Individual Consultants – please complete the table to the best of your knowledge.

| Please Mark ‘X’ In the Relevant Box | Yes | No |
| --- | --- | --- |
| - Conspiracy as defined by the legislative or judicial bodies in your jurisdiction. | s | x |
| - Corruption as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - Bribery as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - The offence of cheating the Revenue as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - The offence of conspiracy to defraud as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - Fraud as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - Theft as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - Fraudulent trading as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - Fraudulent evasion as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - Destroying, defacing or concealing of documents or procuring the execution of a valuable security as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - The possession of articles for use in frauds as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - Any offence considered to be Counter Terrorism as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - Money laundering as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - Any Sexual Offences as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - Drug trafficking as defined by the legislative or judicial bodies in your jurisdiction. |  |  |

- Within the past three years, please indicate if any of the following situations have applied, or currently apply, to you (if an Individual Consultant) or your organisation.

| Please Mark ‘X’ In the Relevant Box | Yes | No |
| --- | --- | --- |
| - You/your organisation is bankrupt or is the subject of insolvency or winding-up proceedings, where your assets are being administered by a liquidator or by the court, where it is in an arrangement with creditors, where its business activities are suspended or it is in any analogous situation arising from a similar procedure under the laws and regulations of any State; |  |  |
| - You/your organisation is guilty of grave professional misconduct, which renders its integrity questionable; |  |  |
| - You/your organisation has entered into agreements with other economic operators aimed at distorting competition; |  |  |
| - the prior involvement of you/your organisation in the preparation of the procurement procedure has resulted in a distortion of competition; |  |  |
| - you/your organisation has shown significant or persistent deficiencies in the performance of a substantive requirement under a prior contract with a contracting entity, or a prior concession contract, which led to early termination of that prior contract, damages or other comparable sanctions. |  |  |

- Employment and Human Rights

For organisations working outside of the UK please refer to equivalent legislation in the country that you are located. Please delete ‘Yes’ / ‘No’ as applicable.

| (a) | In the last three years, has any finding of unlawful discrimination been made against you/your organisation by an Employment Tribunal, an Employment Appeal Tribunal or any other court (or in comparable proceedings in any jurisdiction other than the UK)? | Yes/No |
| --- | --- | --- |
| (b) | In the last three years, have you or has your organisation had a complaint upheld following an investigation by the Equality and Human Rights Commission or its predecessors (or a comparable body in any jurisdiction other than the UK), on grounds or alleged unlawful discrimination? If you have answered “yes” to one or both of the questions, please provide, as a separate Appendix, a summary of the nature of the investigation and an explanation of the outcome of the investigation to date. If the investigation upheld the complaint against your organisation, please use the Appendix to explain what action (if any) you have taken to prevent unlawful discrimination from reoccurring. You may be excluded if you are unable to demonstrate to The Secretariat’s satisfaction that appropriate remedial action has been taken to prevent similar unlawful discrimination reoccurring. | Yes/No |
| (c) | If you use sub-contractors, do you have processes in place to check whether any of the above circumstances apply to these other organisations? | Yes/No/ NA |

- Environmental Legislation

For organisations working outside of the UK please refer to equivalent legislation in the country that you are located. Please delete ‘Yes’ / ‘No’ as applicable.

| (a) | Have you or your organisation been convicted of breaching environmental legislation, or had any notice served upon it, in the last three years by any environmental regulator or authority (including local authority)? If your answer to this question is “Yes”, please provide details in a separate Appendix of the conviction or notice and details of any remedial action or changes you have made as a result of conviction or notices served. The Secretariat will not select bidders that have been prosecuted or served notice under environmental legislation in the last 3 years, unless The Commonwealth is satisfied that appropriate remedial action has been taken to prevent future occurrences/breaches. | Yes/No |
| --- | --- | --- |
| (b) | If you use sub-contractors, do you have processes in place to check whether any of these organisations have been convicted or had a notice served upon them for infringement of environmental legislation? | Yes/No/ NA |

- Health and Safety legislation

For individuals/organisations working outside of the UK please refer to equivalent legislation in the country that you are registered in and/or located. Please delete ‘Yes’ / ‘No’ as applicable.

| (a) | Please self-certify that your organisation has a Health and Safety Policy that complies with current legislative requirements. | Yes/No/NA (individual consultant) |
| --- | --- | --- |
| (b) | Has your organisation or any of its Directors or Executive Officers been in receipt of enforcement/remedial orders in relation to the Health and Safety Executive (or equivalent body) in the last 3 years? If your answer to this question was “Yes”, please provide details in a separate Appendix of any enforcement/remedial orders served and give details of any remedial action or changes to procedures you have made as a result. The Secretariat will exclude bidder(s) that have been in receipt of enforcement/remedial action orders unless the bidder(s) can demonstrate to The Secretariat’s satisfaction that appropriate remedial action has been taken to prevent future occurrences or breaches. | Yes/No/NA (individual consultant) |
| (c) | If you use sub-contractors, do you have processes in place to check whether any of the above circumstances apply to these other organisations? | Yes/No/ NA (individual consultant) |

- Insurance requirements (for information)

Does the Consultant (whether an Individual or Company) have insurances (as may be necessary or relevant by the subject matter of the contract specified in the ToR in this RFQ), currently in place, for the business activities they are proposing to carry out?

YES

NO

3

If Yes, please state the type of insurance and level of insurance held:

| Area | Does the Consultant/supplier have insurances in place? | Level of cover expected | Level of cover currently held |
| --- | --- | --- | --- |
| e.g. Public liability | Yes/No/NA | £5m |  |
| e.g. Employer’s liability | Yes/No/NA | £2m |  |
| e.g. Professional Indemnity | Yes/No/NA | £1m |  |
| e.g. Data Protection Liability (for relevant projects only, where the supplier will be handling/processing personal data on behalf of the Secretariat) | Yes/No/NA | £500K |  |

Please note that the Individual Consultant will not be excluded from the tender process if the answer is ‘No’. However, it is industry best practice for consultants to ensure they have suitable insurances in place for the work they are proposing to undertake.

Please note that the insurance cover detailed above should be in place before activities commence in pursuance of the services required (if successful) and will not be considered as part of the costs under the contract between the Secretariat and the selected consultant.

- Terms and Conditions/Code of Ethics/Corporate Policies

Please delete ‘Yes’ / ‘No’ as applicable.

| (a) | Please confirm that you (if an Individual Consultant)/your organisation agrees to the Commonwealth Secretariat’s: 1. Secretariat’s standard terms and conditions for below £30,000 total contract value can be found at: https://thecommonwealth.org/terms-and-conditions 2. Secretariat’s Code of Ethics and Safeguarding Policy at: https://thecommonwealth.org/corporate-policies and 3. Secretariat’s Corporate policies applicable to Consultant/suppliers and as published from time to time on the following web page: https://thecommonwealth.org/corporate-policies ………………………………………………………………………………………………………………….. If you do not agree to abide by the above, please state reasons and/or changes requested as part of your bid: | Yes/No |
| --- | --- | --- |

- Legal comments table

By submitting a response, the bidder is agreeing to be bound by the terms of this RFQ and the Contract save as in relation to those areas of the Contract specifically highlighted below.  As such, if the terms & conditions of the Commonwealth Secretariat Terms and Conditions | Commonwealth (thecommonwealth.org) renders proposals in the bidder’s response unworkable, the bidder must submit full details of the unworkable/unacceptable provisions within the relevant Standard Terms and Conditions (Consultancy) by completing the Legal Comments Table below.

| Clause/Paragraph /Schedule | Summary of Issue | Suggested Revisions |
| --- | --- | --- |

Part 3 – Technical Questionnaire

The following scoring mechanism will be used to score each question in this section:

| Using a 0 – 5 scoring system: |  |
| --- | --- |
| 0 | Unacceptable Response – No information provided or response does not address the requirement. |
| 1 | Poor response – The response contains material omissions and / or is supported by limited evidence / examples. Concerns that the organisation does not have the potential to deliver / that they have failed to meet a reasonable standard. |
| 2 | Fair response – There is adequate detail / supporting examples giving a reasonable level of confidence in the Tenderer’s experience and ability. The Tenderer appears to have the potential to deliver as required / has met a reasonable standard and there are only minor concerns about the Tenderer’s experience |
| 3 | Good Response – The level of detail / supporting examples gives a high level of confidence in the Tenderer’s experience and ability. The Tenderer clearly has the potential to deliver and / or has clearly met an acceptable standard. |
| 4 | Excellent Response – A comprehensive well evidenced submission, clearly demonstrating expertise and knowledge incorporating some value-added benefits attributes & other points of innovation. The bid is deemed to offer little risk and fully captures the understanding of the steps involved to deliver aspects of the service which can be related to the question posed, giving a high level of confidence in the Tenderer’s experience and ability. |
| 5 | Exceptional Response – A comprehensive and exceptionally evidenced submission that substantially exceeds the expectations of the requirement and offers significant additional benefits. Submission clearly demonstrates exceptional expertise and knowledge incorporating value added benefits/ & other points of innovation. The bid is deemed to offer well identified risks and a mitigation of these put forward and fully captures the understanding of the steps involved to deliver all the aspects of the service and is directly relatable to the question posed, giving an exceptionally high level of confidence in the Tenderer’s experience and ability. |

- The technical questions below are worth 70% of the total score. The individual question weightings are set out in the weighting column.

- The following formula will be applied for each question:

  - Points Scored ÷ Points Available × % weighting

  - The scores for each of the questions will be added to give a total Technical/Quality Score

- Unanswered questions or sections that are left blank shall be awarded a 0.

Please answer all questions in the spaces provided. Please do not attach documents or appendices.

| Question No. | Question | Weighting |
| --- | --- | --- |
| 1 | Understanding the requirement: How do you understand the importance of regulatory coherence in both conventional and digital sectors for enhancing trade in the Indo-Pacific region? - What are the key regulatory challenges you anticipate in the selected countries (Australia, New Zealand, Samoa, Fiji, India, and Malaysia)? - How does your approach align with the objectives and scope of this study? | 20% |
| Insert your answer here |  |  |
| 2 | Methodology Please describe the methodology you propose for conducting the country-specific analysis of the regulatory frameworks. How will you identify and address regulatory barriers in both conventional and digital sectors? - How will you ensure the inclusion of stakeholder consultations in the analysis process? - How do you propose to develop the roadmap for regulatory coherence, and what specific steps will you take to ensure it is actionable and effective? | 20% |
| Insert your answer here |  |  |
| 3 | Experience: Can you provide examples of similar consultancy projects where you have developed regulatory frameworks or conducted policy analysis, particularly in both conventional and digital trade? - What relevant experience do you have in working with international organizations or on projects in the Indo-Pacific region? - How has your work contributed to regulatory coherence in past projects? | 30% |
| Insert your answer here |  |  |
| 4 | Practical skills - What practical skills do you bring to this project, specifically in conducting complex regulatory analysis and stakeholder engagement? - How do you ensure clear and effective communication in both written reports and presentations to diverse stakeholders? - Please provide examples where your practical skills helped in achieving successful outcomes for similar projects. | 20% |
| Insert your answer here |  |  |
| 5 | Education and Qualification - At least ten years’ experience working on developing regulatory frameworks, policy analysis, and impact assessments of regulatory frameworks is required. - A master’s degree in economics, public policy, finance or related field is required (A Bachelor’s degree would be accepted in lieu of a Master’s degree with an additional two years relevant experience) | 10% |
| Insert your answer here |  |  |

Part 4 – Pricing

Transparent pricing must be submitted with no hidden costs. Pricing and cost must be broken down to the different elements of the services and any other costs.

Please complete the Pricing Schedule and submit as a separate document. Please refer to Instructions to bidders which states that unless indicated otherwise, all prices should be quoted in Pounds Sterling.

Consultants are expected (within their financial proposal) to provide a full breakdown of the number of experts/number of days (total and per expert) needed to complete the assignment.

Consultants are to give an indication as to which Band each Consultant’s fee falls within in the Secretariat’s Technical Assistance Consultants: Corporate Fee Band Table (see Annex 1). Include CVs of all staff proposed. Please note that the maximum daily fee rates can not normally exceed £700.

| [For TAP Consultancy: Consultant’s Name/Role/Band – refer to Annex 1 Technical Assistance Consultants: Corporate Fee Band Table] Experts name/role |  | Day Rate (including all taxes) | No of Days | Total (including all taxes) GBP |
| --- | --- | --- | --- | --- |
| Total |  |  |  |  |

If expenses are applicable for this assignment, insert the following table:

| Expenses: |  |  |  |
| --- | --- | --- | --- |
| Per diem (to be in line with Secretariat’s policies on travel and per diem rates) |  |  |  |
| Travel (to be in line with Secretariat’s travel policies) |  |  |  |
| Other (please list) |  |  |  |
| Total in GBP |  |  |  |

For Consultancy: The following scoring mechanism may be used to score the Pricing Section in the Evaluation Matrix to reflect the Fee band (Annex 1) in addition to the Fixed cost score of the project

|  | Using 1-3 Scoring system for Fee Band Requirement |
| --- | --- |
| 1 | Does not meet the fee band requirement |
| 2 | Partially meets the fee band requirement |
| 3 | Fully meets the the fee band requirement |

Payments will be made upon successful completion of the milestones described in the terms of reference, upon receipt of the Secretariat’s written approval of all agreed deliverables and upon submission of a compliant invoice. If there is a VAT element - for UK VAT registered consultant only – this must be itemised in the total quote received/agreed by the Secretariat and the consultant must submit a UK VAT registration certificate to the Secretariat when invoicing. All invoices will be sent to contract manager connectivity@commonwealth.int

Annex 1 – Secretariat’s Technical Assistance Consultants: Corporate Fee Band Table

The consultancy fee rate range associated with a particular level of assignment may be based on the following:

- Knowledge, qualifications, experience, and skills required.

- Level of work in terms of responsibilities and complexity of the assignment.

- Degree of specialization required by the assignment.

| Band | Per Day (GBP) | Comments and Guidelines |
| --- | --- | --- |
| A* | 700+ | - Extensive achievement in their specialist field, in which they are nationally or internationally renowned. Extensive experience of leading or directing major, complex and business-critical projects, bringing genuine strategic insight, understanding the range of services to be delivered. In depth knowledge of the international sector/specialist field and of current policy and political issues affecting it. - Contributions to the accomplishment of a crucial programme or service or functional area of a broad scope, involving high complexity and impact. - Providing functional leadership and expert advice. - Preparing intricate and complex technical papers to working groups. - Undertaking the drafting of reports or proposals for projects of a large scale or a broad scope. - Large-scale programmatic and operational activities involving large commitments of staff and funds. - Rare specialization - Industry equivalent level: Partner/Managing Director |
| B | 500-699 | - Substantial experience in their specialist field and operating multiple major consultancy assignments achieving specific revenue and income objectives to agreed outcomes. - Within this category the person is expected to have significant, proven, industry recognised experience. - Expected to develop new approaches, techniques, or policies and/or design guidelines, standard operating procedures. - Providing technical support; leading group dynamics; and undertaking report drafting or project-wide proposals. - Industry equivalent level: Principal/Senior Consultant |
| C | 350 - 499 | - Demonstrable experience and relevant exposure in a range of projects in a specialist field. - Evidence of client facing experience and relationship management. - Support for planning and monitoring budgets and services to wider consultancy projects; and experience of proposal preparation. - Industry equivalent level: Consultant |
| D | 300-349 | - Specialized degree or training and - Several years of relevant experience - Industry equivalent level: Junior Consultant |
| E | £100 - £299 | - This level is established for the engagement of support services not available in the Secretariat related to projects or technical tasks of a narrow scope for which limited technical skills or experience are required. - Industry equivalent level: Project Support |

https://thecommonwealth.org/corporate-policies

https://thecommonwealth.org/corporate-policies

This will go some way to mitigate against bidders selecting the references that are likely to be more favorable and will assist in providing a more realistic reflection of performance.