COMMONWEALTH SECRETARIAT

MARLBOROUGH HOUSE, PALL MALL, LONDON SW1Y 5HX

IN STRICT COMMERCIAL CONFIDENCE

Request for Quotations (RFQ) for Commonwealth Election Professionals (CEP) Initiative Goods and Services (including Consultancy) for requirements between £5,001 and below £30,000 over life of contract

For the provision of:

Consultancy services to to prepare and conduct training for senior election officials through a series of three regional training events on the application of Artificial Intelligence (AI) in electoral management

February 2026

| Secretariat Reference Number: | ESS/GPD/2026/01 |
| --- | --- |
| Return Date: | Return Date – 12 Noon GMT on Friday 6 March 2026 |
| Estimated Contract Award: | 20 March 2026 |

Contents

1.	Introduction	3

2.	Purpose	3

3.	Instructions to Bidders	3

4.	Evaluation Weightings	3

5.	Quote Timeline	3

6.	Information for Bidders	4

7.	Terms of Reference	5

Part 1 – Bidder Details	8

Part 2 - Suitability Assessment Questions	9

Part 3 – Technical Questionnaire	13

Part 4 – Pricing	14

5. Pricing	15

# Introduction

The Commonwealth Secretariat (The Secretariat) is an international organisation established by Agreed Memorandum, which is given privileges and immunities under the domestic law of the United Kingdom by the Commonwealth Secretariat Act 1966 (as amended by the International Organisations Act 2005). Under this legislation, the Secretariat is not subject to UK jurisdiction and enforcement.

This status has an impact on some of our standard terms and conditions. In particular, we draw your attention to our dispute resolution clause, which refers disputes to the exclusive jurisdiction of the Commonwealth Secretariat Arbitration Tribunal (CSAT). The 8 members of the Tribunal are selected by the Board of Governors and come from Commonwealth member countries. Information about CSAT, including its governing statute and procedure are available on its website at http://thecommonwealth.org/tribunal.

The Secretariat implements decisions agreed by 56 Heads of Government and Ministers through advocacy, consensus–building, information sharing, analysis, technical assistance, capacity-building, and advice on policy development.

# Purpose

The purpose of this request for a quote (RFQ) is to find and appoint a suitable consultant for the provision of Consultancy service to prepare and conduct training for senior election officials through at three Commonwealth Election Professional (CEP) Initiative regional training events on the application of Artificial Intelligence (AI) in electoral management. The appointed consultant shall be awarded a contract that will be effective for up to eighteen (18) months.

Note that the date and location of the first regional training event (for the Commonwealth Caribbean & Americas) is confirmed for Port of Spain, Trinidad and Tobago, from 20 – 24 April 2026. The two further training events will take place within the Commonwealth Africa and Pacific regions respectively before the end of 2027, noting that dates and locations are to be confirmed.

See Terms of Reference in Section 7 for details on the services required.

# Instructions to Bidders

This is a one stage RFQ process with a written submission to this RFQ followed by bidder clarifications, if required. Bidders will be scored following the first stage and if required bidders may be asked to attend a clarification of their Quote meeting.

Bidders must submit all documents as set out in Part1 – Part 5 ‘Quote’ no later than the return date of: 12 Noon GMT on Friday 6 March 2026. The quote documents are to be returned to the following email address: cep@commonwealth.int

Following all stages of the Quote process, the quote received that is deemed as offering best overall value to the Commonwealth Secretariat, shall be awarded the contract based on the notified evaluation weightings:

# Evaluation Weightings

Quality: 100%

# Quote Timeline

Please note, that the following timeline is an estimate and may change at short notice.

| Activity | Date |
| --- | --- |
| Request for quote (RFQ) issued | 20/02/2026 |
| Clarification questions to be submitted by bidders by | 12 Noon GMT on 27/02/2026 |
| Secretariat’s response to (anonymised) clarification questions will be circulated to all in writing by | 03/03/2026 |
| Quotes submission closing date | 12 Noon GMT on 06/03/2026 |
| Evaluation process duration (including any clarification meetings) | 09/03/2026 to 13/03/2026 |
| Contract Start Date | 01/04/2026 |

# Information for Bidders

- Unless indicated otherwise, all prices should be quoted in Pounds Sterling.

- The bidder must ensure that they have all the information required for the preparation of the Quote submission and that they are satisfied about the correct interpretation of terminology used in this documentation. The bidder must also ensure that they are fully conversant with the nature and extent of the obligations should the Quote be accepted.

- Quotes are to be valid for a minimum of 30 days from the closing date for the submission of the Quotes.

- The Commonwealth Secretariat reserves the right to cancel the RFQ at any time during the process and not to award a contract as a result of this procurement.

- Bidders shall bear all costs in completing a quotation submission.

- Bidders shall not disclose details of the RFQ to third parties without prior agreement from an authorised officer of the Commonwealth Scretariat.

- All clarification queries must be submitted by 12 Noon GMT on 27/02/2026 and only to Jonathon Milligan, CEP Programme Officer, at cep@commonwealth.int

- Bidders are required to submit transparent pricing with no hidden costs or charges.

- The Secretariat will carry out an evaluation of the quotes using the weighted criteria method as described. Following the evaluation stage(s) the Secretariat will select a preferred bidder which will be taken forward to contract award. The Secretariat reserves the right to appoint a reserve preferred bidder which the Secretariat could then take forward to contract award if any contract negotiations with the preferred bidder are unsuccessful.

By taking part in this request for quotes all bidders commit to the following:

- Bidders confirm that by submitting a quote they agree to abide by the Secretariat’s Code of  Ethics and relevant Corporate policies as published from time to time on the following web page:

https://thecommonwealth.org/corporate-policies

- Bidders certify that they have not canvassed or solicited any officer or employee of the Secretariat in connection with this Quote submission and that no person employed or acting on behalf of the bidder has done any such act.

- The CSAT shall have exclusive jurisdiction to settle any dispute or claim that arises out of or in connection with this Procurement (including non-contractual disputes or claims).

- Compliance with policies: The Secretariat has a zero-tolerance approach towards sexual exploitation, abuse and harassment. The bidder must familiarise itself with the Secretariat’s policies available at https://thecommonwealth.org/corporate-policies  Particularly with reference to the Anti-Bribery and the Safeguarding Policy, the bidder must understand the obligations imposed on Suppliers/Consultants and their personnel and sub-contractors including having robust procedures to detect and report any wrongdoing or concerns. Adherence to the Secretariat policies is mandatory and if awarded a contract, the Supplier/Consultant will be required to ensure continued compliance with the policies for the duration of the contract.

# Terms of Reference (ToR)

| Consultancy Title | Elections & Training Expert |
| --- | --- |
| Project | Commonwealth Election Professionals (CEP) Initiative |
| Organisational Unit | Electoral Support Section (ESS) / Governance and Peace Directorate GPD / Commonwealth Secretariat |
| Duty Station | Home Based/Field Based |
| Proposed period | April 2026 – December 2027 |
| Consultancy Days | Up to 36 workdays within the proposed period (12 days per each of the three training events) |

________________________________________________________________________________

Background and Introduction

The Commonwealth Election Professionals (CEP) Initiative is an Australian funded project which provides professional development, peer support, knowledge sharing and networking opportunities to Election Management Body (EMB) officials across the Commonwealth through the conduct of in-person and virtual training events. In this way, the CEP Initiative supports Commonwealth EMBs in their work of delivering transparent, credible and inclusive electoral processes.

In its selection of thematic areas, the CEP Initiative focuses on emerging and topical issues of maximum value, benefit and relevance to participating EMBs. The emerging and rapidly evolving impact of Artificial Intelligence (AI) on elections and electoral administration has been highlighted by EMBs across the Commonwealth as an issue of particular interest.

This document sets out the terms of reference to guide the work of the consultant(s) engaged by the Commonwealth Secretariat (“the Secretariat”), to develop training materials and conduct training for three (five-day) CEP Initiative training events, to be held for senior election officials in the following Commonwealth regions:

- Commonwealth Caribbean & Americas: co-hosted by the Election and Boundaries Commission of Trinidad and Tobago, the training will take place in Port of Spain from 20 – 24 April 2026. (NB. These dates are fixed and non-negotiable - applicants must confirm their availability for the travel period 15 to 26 April 2026).

- Commonwealth Africa: Dates and location to be confirmed but by end of 2027.

- Commonwealth Pacific: Dates and location to be confirmed but by end of 2027.

In terms of thematic area, all three regional training events will explore issues relating the application of Artificial Intelligence (AI) to electoral management, tailored to the specific context of each region and application of lessons learned (e.g. methodology, content and participant engagement) on an ongoing basis.

Scope of the Requirement

The Commonwealth Secretariat seeks a consultant to design and conduct a high-quality training programme and related training materials – expert presentations, case studies and group exercises - on the application of AI to electoral management for three regional CEP Initiative training events.

Under the overall supervision of the Head of the Electoral Support Section or their delegate, the Elections & Training Expert will bring their experience and understanding of electoral administration, Artificial Intelligences, and international standards for the conduct of transparent, credible and inclusive elections, to bear in providing a platform for participating Commonwealth election professionals to share experience and emerging good practice.

Noting that continuity in selection of the consultant across the three training events is expected to result in a more cohesive and impactful training programme, the consultant will be required to:

- Design and develop a training programme on the application of AI to electoral management, tailored to the specific context of each of the three Commonwealth regions.

- Develop related training materials, including expert presentations, case studies and group exercises to carry out the deliverables for the three CEP regional training events.

- Conduct and facilitate the training programme for the three CEP regional training events.

- Ensure timely delivery of training materials in accordance with the timelines below.

- Ensure quality control of training deliverables.

- Apply lessons learned in terms of training programme design and content, methodology and participant engagement to subsequent training events.

- Work collaboratively with staff of the Commonwealth Secretariat and other key stakeholders.

Deliverables & Timeline

Please note: The deliverables listed below apply to the April 2026 Commonwealth Caribbean & Americas training event only. The deliverables and timelines for the remaining two training events will be set in due course and once dates and locations have been confirmed.

| Deliverables for CEP Training Event #1: Caribbean & Americas | Timeline |
| --- | --- |
| - Draft outline of training programme and synopsis of content (incl. agenda, methodology, expert presentations, case studies and group exercises). | 06/04/2026 |
| - Presentation of second draft training content (incl. agenda, methodology, expert presentations, case studies, group exercises and recommended readings for Participant Handbook). | 13/04/2026 |
| - Submission of final training materials, which fully incorporates and reflects feedback provided by the Secretariat and other key stakeholders. | 17/04/2026 |
| - Conduct and facilitate and the regional training event for senior election officials. | 20 – 24 April 2026 |

# List of Deliverables/Payment schedule:

The tasks associated with this Terms of Reference are expected to be completed over a contract period beginning April 2026 and ending in December 2027.

For each training event, the consultant will receive professional fees of up to GBP 6,600, based on a daily rate of GBP 550 per day for a maximum of 12 days. Payments will be made based on completion of the deliverables within the table below.

On this basis and in total, the consultant will receive professional fees of up to GBP 19,800 (including VAT and other charges), based on a daily rate of GBP 550 per day for a maximum of 36 days, for the series of three training events.

|  | % | GBP | Deliverable | Due Date |
| --- | --- | --- | --- | --- |
| Payment #1 | 50% | 3,300 | 1a) Acceptance of a draft training programme | 06/04/2026 |
|  |  |  | 1b) Acceptance of synopses the training programme’s related content, including expert presentations, group exercises and other training programme content | 13/04/2026 |
| Payment #2 | 50% | 3,300 | 2a) Satisfactory completion of the conduct of the five-day training event | 20/04/2026 to 24/04/2026 |
|  |  |  | 2b) Acceptance of the Consultant’s contribution to the training event final report | 08/05/2026 |
| TOTAL | 100% | 6,600 |  |  |

# Contract Management

The successful consultant will report to the Secretariat’s Contract Manager: Jonathon Milligan, CEP Programme Manager (ESS/GPD). Email: cep@commonwealth.int

# 10. Skills and experience required

Education and Experience

- Post-graduate degree in Political Science, International Relations, Law, Public Administration, or related field.

- Demonstrable experience and understanding of electoral administration, operations and processes in Commonwealth regions (Africa, Caribbean and Americas, and Pacific), whether through professional work experience, election observation, consultancies or other relevant activities.

- Experience and expertise in designing and delivering training, ideally within an election’s context, with a proven ability to facilitate workshops and develop highly interactive and participatory presentations and activities.

- Demonstrable knowledge and understanding of international standards for the conduct of transparent, credible and inclusive electoral processes.

- Demonstrable knowledge and understanding of Artificial Intelligence (AI) technologies, policy and regulatory and ethical frameworks.

Language

- The working language of the Commonwealth is English: a high-level of spoken and written English is an essential requirement for this role.

Knowledge, Skills and Abilities

- Strong research, design and content development skills, including capacity to develop structured, targeted and engaging training programmes.

- Highly developed written and oral communication skills, including ability to develop and deliver presentations and facilitate meetings for senior officials.

- Ability to work with a high degree of accuracy and attention to quality and detail on complex assignments.

- Sound organisational and planning skills, including proven ability in meeting strict deadlines.

- Flexibility to adapt to any subsequent changes in the terms of reference.

- Strong interpersonal and communication skills and ability to work constructively with internal and external stakeholders.

- Openness to change and ability to receive/integrate feedback.

- Good team player, positive attitude, flexible and comfortable working in multi-cultural settings.

This consultancy assignment is expected to require a Consultant at Band B of the Secretariat’s Technical Assistance Consultants: Corporate Fee Band Table (see Annex 1 Below).

# 11.  Evaluation criteria

The Technical Questionnaire Quotes will be assessed based on the evaluation criteria set forth in this document (see skills and experience required and the weightings apportioned to quality/price above in this Terms of reference).

Part 1: Bidder’s details is for information only.

Part 2: Suitability Assessment Questions -will be assessed on a Pass/Fail basis.

# 12. Conflicts of interest

The consultant shall establish and maintain appropriate business standards, procedures and controls including those necessary to avoid any real or apparent impropriety or to prevent any action or conditions which could result in conflict with the Secretariat’s best interests.

If either Party becomes aware of any actual or possible conflict between the interests of the Secretariat and the Consultant, it shall notify the other Party as soon as reasonably possible and the Parties shall meet to discuss the Conflict and shall: (i) use all reasonable endeavours to find ways to eliminate or minimise the risk of the Conflict; and (ii) take such steps as may be agreed to remove or avoid the cause of the Conflict.

# 13.  Payments

Payments will be made in line with the schedule of deliverables outlined above and upon successful completion of the milestones, upon receipt of the Secretariat’s written approval of all agreed deliverables and upon submission of a compliant invoice and any other supporting documents as may be required by the Secretariat from time to time. All invoices to be sent to contract manager cep@commonwealth.int .

Quote Submission Documents (ESS/GPD/2026/01)

Note - Bidders must complete and return all Quote submission documents below:

Part 1 – Bidder Details

Part 2 – Suitability Assessment Questions

Part 3 – Technical Questionnaire

Part 4 – Pricing

Part 1 – Bidder Details (for information)

Please provide details relating to your registered offices, legal status and date of incorporation.

| Individual/ Company and/or Trading Name |  |  |  | Company/Sole Trader Registration Number |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Company Address |  |  |  | Date of incorporation |  |  |
| Post Code |  |  |  |  |  |  |
| Contact Name |  |  |  | Job Title |  |  |
| Telephone |  |  |  | Email |  |  |
| In the event of utilising a third party, on your behalf for any part of the services, please provide the full details of the secondary consultant/supplier: |  |  |  |  |  |  |
| Company Name |  |  |  | Duration of working relationship, |  |  |
| Company Address |  |  |  | Reason for use |  |  |
| Post Code |  |  |  |  |  |  |
| In line with the Secretariat’s Procurement Code of Ethics, the Secretariat works towards encouraging SMEs to apply for relevant tenders and is committed to monitoring the environmental awareness of our consultants, suppliers and partners with a view (where relevant to the subject matter of the contract) to only doing business with ISO 14001 Environmental Management or ISO 50001 Energy Management accredited organisations. |  |  |  |  |  |  |
| Is the Consultant classified as a Micro or Small Medium Enterprise (SME)?; Yes/No. Is the Consultant an ISO14001 or ISO 50001 (Energy Management) accredited organisation?; Yes/No. UK VAT Declaration For UK Registered consultant: Is the bidder registered for Value Added Tax (VAT)? [Y/N] If Yes, please include VAT registration number [insert] and provide a copy of your VAT registration certificate as part of your response. |
| Please note, the successful bidder (if a company and not an Individual) may also be checked for their Equifax Financial Credit Score. Should the bidder (if a company) fail the commercial credit score check, the Secretariat will be entitled to commence negotiations with the second preferred bidder subject to that bidder (if a Company) having passed the Equifax Credit Score and so forth. Please provide the contact details of two reference clients. A minimum of two references will be collected from previous clients (excluding the Secretariat) from projects carried out in (max) last 18 months. Please provide references from similar international organisations or public sector bodies or equivalent if possible. One of the references should relate to the most recent contract you/your company has fulfilled. If possible, additionally, supply a list of potential references from which the Secretariat can select the referees they wish to contact. The referees will not be contacted until the final stage of the Quote process. |  |  |  |  |  |  |
|  |  | Reference 1 |  |  | Reference 2 |  |
| Company Name |  |  |  |  |  |  |
| Company Address |  |  |  |  |  |  |
| Post Code |  |  |  |  |  |  |
| Referees name |  |  |  |  |  |  |
| Referee Telephone |  |  |  |  |  |  |
| Referee Email |  |  |  |  |  |  |

Part 2 - Suitability Assessment Questions (pass/fail)

Grounds for Exclusion

You will be excluded from the Quote process if there is evidence of convictions relating to specific criminal offences including, but not limited to, bribery, corruption, conspiracy, terrorism, fraud and money laundering, or if you have been the subject of a binding legal decision which found a breach of legal obligations to pay tax or social security obligations.

- Within the past five years, have you or your organisation (or any member of your proposed consortium, if applicable)- if you are trading as a company - Directors or Partner or any other person who has powers of representation, decision or control been convicted of any of the following offences? Individual Consultants – please complete the table to the best of your knowledge.

| Please Mark ‘X’ In the Relevant Box | Yes | No |
| --- | --- | --- |
| - Conspiracy as defined by the legislative or judicial bodies in your jurisdiction. | s | x |
| - Corruption as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - Bribery as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - The offence of cheating the Revenue as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - The offence of conspiracy to defraud as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - Fraud as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - Theft as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - Fraudulent trading as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - Fraudulent evasion as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - Destroying, defacing or concealing of documents or procuring the execution of a valuable security as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - The possession of articles for use in frauds as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - Any offence considered to be Counter Terrorism as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - Money laundering as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - Any Sexual Offences as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - Drug trafficking as defined by the legislative or judicial bodies in your jurisdiction. |  |  |

- Within the past three years, please indicate if any of the following situations have applied, or currently apply, to you (if an Individual Consultant) or your organisation.

| Please Mark ‘X’ In the Relevant Box | Yes | No |
| --- | --- | --- |
| - You/your organisation is bankrupt or is the subject of insolvency or winding-up proceedings, where your assets are being administered by a liquidator or by the court, where it is in an arrangement with creditors, where its business activities are suspended or it is in any analogous situation arising from a similar procedure under the laws and regulations of any State; |  |  |
| - You/your organisation is guilty of grave professional misconduct, which renders its integrity questionable; |  |  |
| - You/your organisation has entered into agreements with other economic operators aimed at distorting competition; |  |  |
| - the prior involvement of you/your organisation in the preparation of the procurement procedure has resulted in a distortion of competition; |  |  |
| - you/your organisation has shown significant or persistent deficiencies in the performance of a substantive requirement under a prior contract with a contracting entity, or a prior concession contract, which led to early termination of that prior contract, damages or other comparable sanctions. |  |  |

- Employment and Human Rights

For organisations working outside of the UK please refer to equivalent legislation in the country that you are located. Please delete ‘Yes’ / ‘No’ as applicable.

| (a) | In the last three years, has any finding of unlawful discrimination been made against you/your organisation by an Employment Tribunal, an Employment Appeal Tribunal or any other court (or in comparable proceedings in any jurisdiction other than the UK)? | Yes/No |
| --- | --- | --- |
| (b) | In the last three years, have you or has your organisation had a complaint upheld following an investigation by the Equality and Human Rights Commission or its predecessors (or a comparable body in any jurisdiction other than the UK), on grounds or alleged unlawful discrimination? If you have answered “yes” to one or both of the questions, please provide, as a separate Appendix, a summary of the nature of the investigation and an explanation of the outcome of the investigation to date. If the investigation upheld the complaint against your organisation, please use the Appendix to explain what action (if any) you have taken to prevent unlawful discrimination from reoccurring. You may be excluded if you are unable to demonstrate to The Secretariat’s satisfaction that appropriate remedial action has been taken to prevent similar unlawful discrimination reoccurring. | Yes/No |
| (c) | If you use sub-contractors, do you have processes in place to check whether any of the above circumstances apply to these other organisations? | Yes/No/ NA |

- Environmental Legislation

For organisations working outside of the UK please refer to equivalent legislation in the country that you are located. Please delete ‘Yes’ / ‘No’ as applicable.

| (a) | Have you or your organisation been convicted of breaching environmental legislation, or had any notice served upon it, in the last three years by any environmental regulator or authority (including local authority)? If your answer to this question is “Yes”, please provide details in a separate Appendix of the conviction or notice and details of any remedial action or changes you have made as a result of conviction or notices served. The Secretariat will not select bidders that have been prosecuted or served notice under environmental legislation in the last 3 years, unless The Commonwealth is satisfied that appropriate remedial action has been taken to prevent future occurrences/breaches. | Yes/No |
| --- | --- | --- |
| (b) | If you use sub-contractors, do you have processes in place to check whether any of these organisations have been convicted or had a notice served upon them for infringement of environmental legislation? | Yes/No/ NA |

- Health and Safety legislation

For individuals/organisations working outside of the UK please refer to equivalent legislation in the country that you are registered in and/or located. Please delete ‘Yes’ / ‘No’ as applicable.

| (a) | Please self-certify that your organisation has a Health and Safety Policy that complies with current legislative requirements. | Yes/No/NA (individual consultant) |
| --- | --- | --- |
| (b) | Has your organisation or any of its directors or Executive Officers been in receipt of enforcement/remedial orders in relation to the Health and Safety Executive (or equivalent body) in the last 3 years? If your answer to this question was “Yes”, please provide details in a separate Appendix of any enforcement/remedial orders served and give details of any remedial action or changes to procedures you have made as a result. The Secretariat will exclude bidder(s) that have been in receipt of enforcement/remedial action orders unless the bidder(s) can demonstrate to The Secretariat’s satisfaction that appropriate remedial action has been taken to prevent future occurrences or breaches. | Yes/No/NA (individual consultant) |
| (c) | If you use sub-contractors, do you have processes in place to check whether any of the above circumstances apply to these other organisations? | Yes/No/ NA (individual consultant) |

- Insurance requirements (for information)

Does the Consultant (whether an Individual or Company) have insurances (as may be necessary or relevant by the subject matter of the contract specified in the ToR in this RFQ), currently in place, for the business activities they are proposing to carry out?

YES

NO

If Yes, please state the type of insurance and level of insurance held:

| Area | Does the Consultant/supplier have insurances in place? | Level of cover expected | Level of cover currently held |
| --- | --- | --- | --- |
| e.g. public liability | Yes/No/NA | £10m |  |
| e.g. Employer’s liability | Yes/No/NA | £5m |  |
| e.g. Professional Indemnity | Yes/No/NA | £1m |  |
| e.g. Data Protection Liability (for relevant projects only, where the supplier will be handling/processing personal data on behalf of the Secretariat) | Yes/No/NA | See below |  |

Please note that the Individual Consultant will not be excluded from the tender process if the answer is ‘No.’ However, it is industry best practice for consultants to ensure they have suitable insurance in place for the work they are proposing to undertake.

Please note that the insurance cover detailed above should be in place before activities commence in pursuance of the services required (if successful) and will not be considered as part of the costs under the contract between the Secretariat and the selected consultant.

- Terms and Conditions/Code of Ethics/Corporate Policies

Please delete ‘Yes’ / ‘No’ as applicable.

| (a) | Please confirm that you (if an Individual Consultant)/your organisation agrees to the Commonwealth Secretariat’s: 1. Secretariat’s standard terms and conditions for below £30,000 total contract value can be found at: https://thecommonwealth.org/terms-and-conditions 2. Secretariat’s Code of Ethics and Safeguarding Policy at: https://thecommonwealth.org/corporate-policies and 3. Secretariat’s Corporate policies applicable to Consultant/suppliers and as published from time to time on the following web page: https://thecommonwealth.org/corporate-policies ………………………………………………………………………………………………………………….. If you do not agree to abide by the above, please state reasons and/or changes requested as part of your bid: | Yes/No |
| --- | --- | --- |

- Legal comments table

By submitting a response, the bidder is agreeing to be bound by the terms of this RFQ and the Contract save as in relation to those areas of the Contract specifically highlighted below.  As such, if the terms & conditions of the Commonwealth Secretariat Terms and Conditions | Commonwealth (thecommonwealth.org) renders proposals in the bidder’s response unworkable, the bidder must submit full details of the unworkable/unacceptable provisions within the relevant Standard Terms and Conditions (Consultancy or Goods and Services) by completing the Legal Comments Table below.

| Clause/Paragraph /Schedule | Summary of Issue | Suggested Revisions |
| --- | --- | --- |

Part 3 – Technical Questionnaire

The following scoring mechanism will be used to score each question in this section:

| Using a 0 – 5 scoring system: |  |
| --- | --- |
| 0 | Unacceptable Response – No information provided or response does not address the requirement. |
| 1 | Poor response – The response contains material omissions and / or is supported by limited evidence / examples. Concerns that the organisation does not have the potential to deliver / that they have failed to meet a reasonable standard. |
| 2 | Fair response – There is adequate detail / supporting examples giving a reasonable level of confidence in the Tenderer’s experience and ability. The Tenderer appears to have the potential to deliver as required / has met a reasonable standard and there are only minor concerns about the Tenderer’s experience |
| 3 | Good Response – The level of detail / supporting examples gives a high level of confidence in the Tenderer’s experience and ability. The Tenderer clearly has the potential to deliver and / or has clearly met an acceptable standard. |
| 4 | Excellent Response – A comprehensive well evidenced submission, clearly demonstrating expertise and knowledge incorporating some value-added benefits attributes & other points of innovation. The bid is deemed to offer little risk and fully captures the understanding of the steps involved to deliver aspects of the service which can be related to the question posed, giving a high level of confidence in the Tenderer’s experience and ability. |
| 5 | Exceptional Response – A comprehensive and exceptionally evidenced submission that substantially exceeds the expectations of the requirement and offers significant additional benefits. Submission clearly demonstrates exceptional expertise and knowledge incorporating value added benefits/ & other points of innovation. The bid is deemed to offer well identified risks and a mitigation of these put forward and fully captures the understanding of the steps involved to deliver all the aspects of the service and is directly relatable to the question posed, giving an exceptionally high level of confidence in the Tenderer’s experience and ability. |

- The technical questions below are worth 100% of the total score. The individual question weightings are set out in the weighting column.

- The following formula will be applied for each question:

  - Points Scored ÷ Points Available × % weighting

  - The scores for each of the questions will be added to give a total Technical/Quality Score

- Unanswered questions or sections that are left blank shall be awarded a 0.

Please answer all questions in the spaces provided. Please do not attach documents or appendices.

| Question No. | Question | Weighting |
| --- | --- | --- |
| 1 | Understanding the requirement |  |
| 1a | Provide a copy of your CV for review as part of the evaluation process, highlighting your relevant professional experience in relation to the ToR (NB. Please attach your CV to the submission email). | 10% |
| 1b | How do you interpret the objectives of this assignment, and what do you see as the three most critical outcomes the trainings should achieve for Election Management Bodies (EMBs). | 10% |
| Insert your answer here |  |  |
| 2 | Methodology & Approach | 20% |
|  | Walk us through your proposed methodology for designing and delivering the three regional trainings. How will you ensure each training is contextually relevant, participatory and engaging while maintaining consistent quality and learning outcomes? |  |
| Insert your answer here |  |  |
| 3 | Professional Experience |  |
| 3a | Describe your most relevant prior engagement in designing or delivering training for EMBs or electoral stakeholders. What was the scope, who were the participants, and what were the outcomes? | 20% |
| Insert your answer here |  |  |
| 3b | Describe a training or capacity-building assignment you have facilitated that addressed the emerging topic of Artificial Intelligence? (If related to electoral management, please highlight). | 20% |
| Insert your answer here |  |  |
| 3c | What experience do you have working specifically in Africa, the Caribbean and Americas, and the Pacific regions? Please highlight any work directly with EMBs, democratic governance institutions, or international electoral assistance organisations in these regions. | 20% |
| Insert your answer here |  |  |

https://thecommonwealth.org/corporate-policies

This will go some way to mitigate against bidders selecting the references that are likely to be more favorable and will assist in providing a more realistic reflection of performance.

Where contracts involve significant data processing, data protection cap needs to be determined on a case-by-case basis. For low-cost contracts that involve little (emails only) or no data processing, the liability is capped at 1.5 times of the contract value.