COMMONWEALTH SECRETARIAT

MARLBOROUGH HOUSE, PALL MALL, LONDON SW1Y 5HX

IN STRICT COMMERCIAL CONFIDENCE

Request for Quotations (RFQ)

For the Provision of the Consultancy to Analyse Gender Integration in Commonwealth Countries’ NDC 3.0 and Alignment with the Belem Gender Action Plan

March 2026

| Secretariat Reference Number: | CCO/Climate Change/ATE2338/2026 |
| --- | --- |
| Return Date: | Return Date – Noon (BTS) on 31/03/2026 |
| Estimated Contract Award: | April 2026 |

Contents

1.	Introduction	3

2.	Purpose	3

3.	Instructions to Bidders	3

4.	Evaluation Weightings	3

5.	Quote Timeline	4

6.	Information for Bidders	4

7.	Specification of Requirements/Terms of reference	5

Part 1 – Bidder Details	8

Part 2 - Suitability Assessment Questions	9

Part 3 – Technical Questionnaire	13

Part 4 – Pricing	14

# Introduction

The Commonwealth Secretariat (The Secretariat) is an international organisation established by Agreed Memorandum, which is given privileges and immunities under the domestic law of the United Kingdom by the Commonwealth Secretariat Act 1966 (as amended by the International Organisations Act 2005). Under this legislation, the Secretariat is not subject to UK jurisdiction and enforcement.

This status has an impact on some of our standard terms and conditions. In particular, we draw your attention to our dispute resolution clause, which refers disputes to the exclusive jurisdiction of the Commonwealth Secretariat Arbitration Tribunal (CSAT). The 8 members of the Tribunal are selected by the Board of Governors and come from Commonwealth member countries. Information about CSAT, including its governing statute and procedure are available on its website at http://thecommonwealth.org/tribunal.

The Secretariat implements decisions agreed by 56 Heads of Government and Ministers through advocacy, consensus–building, information sharing, analysis, technical assistance, capacity-building, and advice on policy development.

# Purpose

The purpose of this request for a quote (RFQ) is to find and appoint a suitable consultant for the provision of consultancy to analyse gender integration in Commonwealth Countries’ NDC 3.0 and alignment with the Belem Gender Action Plan to the Commonwealth Secretariat. The appointed consultant shall be awarded a contract that will be effective for up to 3 months.

See Terms of Reference in Section 7 for details on the services required.

# Instructions to Bidders

This is a one stage RFQ process with a written submission to this RFQ followed by bidder clarifications, if required. Bidders will be scored following the first stage and if required bidders may be asked to attend a clarification of their Quote meeting.

Bidders must submit all documents as set out in Part1 – Part 5 ‘Quote’ no later than the return date of: noon (BST) on 31/03/2026. [The quote documents are to be returned to the following email address: climatechange@commonwealt.int]

Following all stages of the Quote process, the quote received that is deemed as offering best overall value to the Commonwealth Secretariat, shall be awarded the contract based on the notified evaluation weightings:

# Evaluation Weightings

Quality 100%

Price 0%

# Quote Timeline

Please note, that the following timeline is an estimate and may change at short notice.

| Activity | Date |
| --- | --- |
| Clarification questions to be submitted by bidders by | 22/03/2026 |
| Secretariat’s response to (anonymised) clarification questions will be circulated to all in writing by | 27/03/2026 |
| Quotes submission closing date | 31/03/2026 |
| Evaluation process duration (including any clarification meetings) | 2-3 weeks |
| Contract Start Date | April 2026 |

# Information for Bidders

- Unless indicated otherwise, all prices should be quoted in Pounds Sterling.

- The bidder must ensure that they have all the information required for the preparation of the Quote submission and that they are satisfied about the correct interpretation of terminology used in this documentation. The bidder must also ensure that they are fully conversant with the nature and extent of the obligations should the Quote be accepted.

- Quotes are to be valid for a minimum of [30] days from the closing date for the submission of the Quotes.

- The Commonwealth Secretariat reserves the right to cancel the RFQ at any time during the process and not to award a contract as a result of this procurement.

- Bidders shall bear all costs in completing a quotation submission.

- Bidders shall not disclose details of the RFQ to third parties without prior agreement from an authorised officer of the Commonwealth Scretariat.

- All clarification queries must be submitted by 22/03/2026 (BST).

- The Secretariat will carry out an evaluation of the quotes using the weighted criteria method as described. Following the evaluation stage(s) the Secretariat will select a preferred bidder which will be taken forward to contract award. The Secretariat reserves the right to appoint a reserve preferred bidder which the Secretariat could then take forward to contract award if any contract negotiations with the preferred bidder are unsuccessful.

By taking part in this request for quotes all bidders commit to the following:

- Bidders confirm that by submitting a quote they agree to abide by the Secretariat’s Code of  Ethics and relevant Corporate policies as published from time to time on the following web page:

https://thecommonwealth.org/corporate-policies

- Bidders certify that they have not canvassed or solicited any officer or employee of the Secretariat in connection with this Quote submission and that no person employed or acting on behalf of the bidder has done any such act.

- The CSAT shall have exclusive jurisdiction to settle any dispute or claim that arises out of or in connection with this Procurement (including non-contractual disputes or claims).

- Compliance with policies: The Secretariat has a zero-tolerance approach towards sexual exploitation, abuse and harassment. The bidder must familiarise itself with the Secretariat’s policies available at https://thecommonwealth.org/corporate-policies  Particularly with reference to the Anti- Bribery and the Safeguarding Policy, the bidder must understand the obligations imposed on Suppliers/Consultants and their personnel and sub-contractors including having robust procedures to detect and report any wrongdoing or concerns. Adherence to the Secretariat policies is mandatory and if awarded a contract, the Supplier/Consultant will be required to ensure continued compliance with the policies for the duration of the contract.

# Terms of Reference (ToR)

Project: Consultancy to Analyse Gender Integration in Commonwealth Countries’ NDC 3.0 and Alignment with the Belem Gender Action Plan

1. Background

Global climate governance increasingly recognises that gender-responsive climate action is essential for achieving effective, inclusive and equitable outcomes. Women and girls are often disproportionately affected by climate change due to structural inequalities in access to resources, finance, land, technology and decision-making. At the same time, they play a critical role in advancing climate resilience and sustainable development. While progress has been made through frameworks such as the Enhanced Lima Work Programme on Gender and the UNFCCC Gender Action Plan, the integration of gender across mitigation, adaptation and the means of implementation—including climate finance, technology transfer and capacity-building—remains uneven.

Within the Commonwealth, member states have reaffirmed the importance of gender equality as a central element of sustainable development and resilience. Commonwealth Heads of Government and the Board of Governors have mandated the Secretariat to mainstream gender across all programme and policy work, including through the 2015 CHOGM Communiqué and subsequent institutional strategies. The Commonwealth Secretariat Strategic Plan 2025–2030 further strengthens this commitment by identifying gender equality as a cross-cutting priority across democratic, economic and environmental resilience, recognising that women’s participation, leadership and access to economic opportunities are essential for building resilient societies and economies.

At the global level, initiatives such as the Belém Gender Action Plan have reinforced the importance of gender-responsive climate policies, greater representation of women in climate decision-making, improved access to finance for women-led climate solutions, and stronger monitoring and accountability for gender outcomes in climate action.

The most recent round of Nationally Determined Contributions (NDC 3.0) presents a critical opportunity to support Commonwealth member countries in embedding gender equality within climate commitments. This aligns with evolving requirements of international climate finance mechanisms (the Adaptation Fund, Green Climate Fund and Global Environment Facility) which require gender-responsive project design, implementation and reporting. Key areas include:

- Strengthening gender-responsive climate financing and reporting,

- Enhancing the nomination of gender–climate focal points,

- Supporting countries in identifying gender-responsive actions within NDC 3.0,

- Assessing readiness for gender-responsive monitoring and accountability frameworks, and

- Informing Commonwealth Heads of Government Meeting including Commonwealth Women’s Forum, Rio Convention Conference of Parties and other engagements.

In this context, the Secretariat seeks to undertake a comprehensive analysis of gender integration in Commonwealth Member States’ NDC 3.0 submissions, to guide programming, advocacy, and capacity-building.

2. Objectives

The purpose of this assignment is to analyse gender integration in Commonwealth Member States’ NDC 3.0 submissions and assess alignment with the Belem Gender Action Plan.

- Assess the extent and quality of gender integration in NDC 3.0 submissions.
Review how gender considerations are reflected in climate commitments, enabling conditions, implementation mechanisms, and monitoring approaches under the Paris Agreement.

- Identify progress and trends since earlier NDC cycles.
Analyse changes in ambition and policy alignment since previous NDCs, including uptake of gender-responsive budgeting, participatory processes, and references to gender policies and institutions.

- Review the Belém Gender Action Plan and identify gaps and opportunities.
Assess how Belem GAP priorities under the United Nations Framework Convention on Climate Change are reflected in Commonwealth Countries NDCs and identify areas for strengthening gender-responsive climate action.

- Provide evidence-based recommendations.
Identify capacity gaps, good practices, and opportunities for replication to strengthen gender-responsive climate action and inform updates to Gender Integration in Nationally Determined Contributions: A Commonwealth Best Practice Guide and Gender Integration for Climate Action: A review of Commonwealth Member Countries Nationally Determined Contributions.

3. Scope of Work

The Consultant will work closely with the Climate Change and Gender Sections to undertake the following:

A. Enhance and update the analytical framework report – Gender Integration for Climate Action: A review of Commonwealth Member Country Nationally Determined Contributions (Third Edition)

Building on the previous NDC gender analysis methodology, refine the framework to:

- Integrate indicators appropriate for NDC 3.0,

- Incorporate Gender-responsive Assessment Scales,

- Address links to climate finance access and readiness,

- Reflect contemporary UNFCCC gender-responsive reporting requirements,

- Include justice-oriented elements aligned with CSW 2026’s “access to justice” theme.

B. Conduct a structured analysis of all available NDC 3.0 submissions.

This includes reviewing:

- References to gender equality/women/girls, and broader inclusion considerations including, identifying references to persons with disabilities, youth, Indigenous Peoples, and other groups commonly recognised in international climate and inclusion frameworks.

- Nature of gender commitments (adaptation, mitigation, M&E, implementation, means of implementation),

- Human rights/inclusion framing,

- Positioning of women (vulnerable group, beneficiaries, agents of change, decision-makers),

- Financial commitments and gender-responsive budgeting,

- Participatory/consultative processes,

- References to national gender policies or National Women’s Machinery,

- Conditional vs. unconditional gender actions,

- Readiness for gender–climate focal point engagement.

C. Identify case studies and good practices.

Drawing on NDC 3.0 documentation, Secretariat-supported country programmes, and examples highlighted during internal discussions update Gender Integration in Nationally Determined Contributions: A Commonwealth Best Practice Guide

D. Produce a high-quality synthesis report

Including:

- Overview of trends across the Commonwealth,

- Comparative analysis across regions, income groups, and SIDS/LDC contexts,

- Evidence-based recommendations for Secretariat programme design and member-state support,

- Input to communications products such as briefing notes, high-level talking points, and video storytelling content.

E. Present findings and incorporate feedback

Present the draft analytical findings to the Climate Change and Gender Sections and Regional/National Climate Finance Advisers; integrate comments into a final report. In addition, the Consultant will prepare one to two concise policy briefs (2–3 pages each) synthesising key findings and recommendations from the analysis. These briefs will be tailored for strategic political and financing moments, including the Commonwealth Heads of Government Meeting (CHOGM), UNFCCC Conference of the Parties (COP), and major climate finance dialogues.

4. Amount, Deliverables and Timeline

This assignment renumeration amount is £10,000  VAT inclusive over a 3 month period from 1 April to 30 June. Payment will be made upon successful delivery of deliverables identified below and submission of invoices. The consultancy will be remote/home-based.

| Payment | Deliverable | Timeline |
| --- | --- | --- |
| - | Inception Report outlining understanding of assignment, refined methodology, updated analytical framework for assessing gender integration in NDC 3.0 submissions (including alignment with the Belém Gender Action Plan), and a detailed work plan. | Week 1 |
| 30% | Updated Analytical Framework & draft Policy Briefs. Updated report annotated outline of Gender Integration for Climate Action: A Review of Commonwealth Member Countries’ Nationally Determined Contributions (Third Edition). | Week 4 |
| 30% | Final policy briefs incorporating feedback and Draft Analytical Report - Gender Integration for Climate Action: A review of Commonwealth Member Country Nationally Determined Contributions (Third Edition) -including structured analysis of available NDC 3.0 submissions using the approved framework and identification of emerging trends, gaps, and case studies to inform the update of Gender Integration in Nationally Determined Contributions: A Commonwealth Best Practice Guide. | Week 8 |
| 40% | Final version of Gender Integration for Climate Action: A review of Commonwealth Member Country Nationally Determined Contributions (Third Edition) Report and Commonwealth Best Practise Guide incorporating comments & case studies | Week 12 |

5. Consultant Profile

The Consultant should demonstrate:

- A postgraduate degree (Master’s) in Gender Studies, Climate Change, Environmental Studies and/or related discipline.

- Strong expertise in gender-responsive climate policy, UNFCCC processes, and NDC development.

- At least  7 – 10 years’ experience in gender equality and climate change, preferably in an international development context.

- Expertise in gender analysis, and substantial experience in considering the gender aspects of climate change.

- Excellent analytical and writing skills.

- Fluency in English (required).

6. Contract Management

The consultancy will be managed by the Climate Change Section, with input from the Gender Section. The Consultant will report to the Head, Climate Change.

Should this opportunity be of interest, you are warmly invited to submit an application comprising a curriculum vitae, cover letter and a 5–10 page proposal, including a detailed breakdown of the proposed approach.

8 List of Deliverables/Payment schedule:

This assignment renumeration amount is £10,000  VAT inclusive over a 3 month period from 1 April to 30 June. Payment will be made upon successful delivery of deliverables identified below and submission of invoices. The consultancy will be remote/home-based.

| Payment | Deliverable | Timeline |
| --- | --- | --- |
| - | Inception Report outlining understanding of assignment, refined methodology, updated analytical framework for assessing gender integration in NDC 3.0 submissions (including alignment with the Belém Gender Action Plan), and a detailed work plan. | Week 1 |
| 30% | Updated Analytical Framework & draft Policy Briefs. Updated report annotated outline of Gender Integration for Climate Action: A Review of Commonwealth Member Countries’ Nationally Determined Contributions (Third Edition). | Week 4 |
| 30% | Final policy briefs incorporating feedback and Draft Analytical Report - Gender Integration for Climate Action: A review of Commonwealth Member Country Nationally Determined Contributions (Third Edition) -including structured analysis of available NDC 3.0 submissions using the approved framework and identification of emerging trends, gaps, and case studies to inform the update of Gender Integration in Nationally Determined Contributions: A Commonwealth Best Practice Guide. | Week 8 |
| 40% | Final version of Gender Integration for Climate Action: A review of Commonwealth Member Country Nationally Determined Contributions (Third Edition) Report and Commonwealth Best Practise Guide incorporating comments & case studies | Week 12 |

9 Contract Management

The successful consultant will report to the Secretariat’s Contract Manager [Ms. Uzoamaka Nwamarah, Head of Climate Change, CCO, u.nwamarah@commonwealth.int].

10 Monitoring/ Reporting Requirements

The consultancy firm for this assignment may be international. The consultant will be responsible for his/her own computer equipment, applications and internet connection.

The Climate Change Section will be the owner of the assignment output and will be responsible for providing oversight, quality check and quality assurance necessary to align the output to the government priorities and needs.

The consultant(s) will be accountable to the Climate Change Section.

11 Methodology

Information only – the information provided will not be scored, but failure to provide it may result in the ITT submission being disqualified from the tender process.

Pass/Fail – as indicated in the invitation to tender

12 Skills and Experience Required

Education/ Qualifications:

A postgraduate degree (Master’s) in Gender Studies, Climate Change, Environmental Studies and/or related discipline.

Experience:

Strong expertise in gender-responsive climate policy, UNFCCC processes, and NDC development.

At least  7 – 10 years’ experience in gender equality and climate change, preferably in an international development context.

Language:

The consultancy team should have excellent writing, editing, and oral communication skills in English.

Knowledge, Skills and Abilities

Expertise in gender analysis, and substantial experience in considering the gender aspects of climate change.

Excellent analytical and writing skills.

13 Evaluation criteria

Your curriculum vitae, cover letter and proposal will be assessed based on the evaluation criteria set forth in this document (see skills and experience required and the weightings apportioned to quality/price above in this Terms of reference/RFQ).

Part 1 Bidder’s details is for information only.

Part 2 - Suitability Assessment Questions -will be assessed on a Pass/Fail basis

14 Payments

Payments will be made in line with the schedule of deliverables outlined above and upon successful completion of the milestones, upon receipt of the Secretariat’s written approval of all agreed deliverables and upon submission of a compliant invoice and any other supporting documents as may be required by the Secretariat from time to time. All invoices to be sent to e.poon@commonwealth.int.

Quote Submission Documents (ref CCO/Climate Change/ATE2338/2026)

Note - Bidders must complete and return all Quote submission documents below:

Part 1 – Bidder Details

Part 2 – Suitability Assessment Questions

Part 3 – Technical Questionnaire

Part 4 – Pricing

Part 1 – Bidder Details (for information)

Please provide details relating to your registered offices, legal status and date of incorporation.

| Individual/ Company and/or Trading Name |  |  |  |  | Company/Sole Trader Registration Number |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Company Address |  |  |  |  | Date of incorporation |  |  |  |  |
| Post Code |  |  |  |  |  |  |  |  |  |
| Contact Name |  |  |  |  | Job Title |  |  |  |  |
| Telephone |  |  |  |  | Email |  |  |  |  |
| In the event of utilising a third party, on your behalf for any part of the services, please provide the full details of the secondary consultant/supplier: |  |  |  |  |  |  |  |  |  |
| Company Name |  |  |  |  | Duration of working relationship, |  |  |  |  |
| Company Address |  |  |  |  | Reason for use |  |  |  |  |
| Post Code |  |  |  |  |  |  |  |  |  |
| In line with the Secretariat’s Procurement Code of Ethics, the Secretariat works towards encouraging SMEs to apply for relevant tenders and is committed to monitoring the environmental awareness of our consultants, suppliers and partners with a view (where relevant to the subject matter of the contract) to only doing business with ISO 14001 Environmental Management or ISO 50001 Energy Management accredited organisations. |  |  |  |  |  |  |  |  |  |
| Is the Consultant classified as a Micro or Small Medium Enterprise (SME)?; Yes/No. Is the Consultant an ISO14001 or ISO 50001 (Energy Management) accredited organisation?; Yes/No. UK VAT Declaration For UK Registered consultant: Is the bidder registered for Value Added Tax (VAT)? [Y/N] If Yes, please include VAT registration number [insert] and provide a copy of your VAT registration certificate as part of your response. Annual Turnover check: In line with the Secretariat’s Procurement Code of Ethics, the Secretariat expects for its consultant/suppliers to have a turn over that is, as a minimum, twice the value of the contract they are applying for. Please state the following: |
|  | Annual |  | Previous Year |  |  |  |  | Year 2 |  |
|  | Turnover: |  | £ |  |  |  |  | £ |  |
| Or |  |  |  |  |  |  |  |  |  |
| For individual consultants, please confirm that your annual turnover is twice the value of the Contract you are applying for: YES Please note, the successful bidder (if a company and not an Individual) may also be checked for their Equifax Financial Credit Score. Should the bidder (if a company) fail the commercial credit score check, the Secretariat will be entitled to commence negotiations with the second preferred bidder subject to that bidder (if a Company) having passed the Equifax Credit Score and so forth. Please provide the contact details of two reference clients. A minimum of two references will be collected from previous clients (excluding the Secretariat) from projects carried out in (max) last 18 months. Please provide references from similar international organisations or public sector bodies or equivalent if possible. One of the references should relate to the most recent contract you/your company has fulfilled. If possible, additionally, supply a list of potential references from which the Secretariat can select the referees they wish to contact. The referees will not be contacted until the final stage of the Quote process. |
|  |  | Reference 1 |  |  |  | Reference 2 |  |  |  |
| Company Name |  |  |  |  |  |  |  |  |  |
| Company Address |  |  |  |  |  |  |  |  |  |
| Post Code |  |  |  |  |  |  |  |  |  |
| Referees name |  |  |  |  |  |  |  |  |  |
| Referee Telephone |  |  |  |  |  |  |  |  |  |
| Referee Email |  |  |  |  |  |  |  |  |  |

Part 2 - Suitability Assessment Questions (pass/fail)

Grounds for Exclusion

You will be excluded from the Quote process if there is evidence of convictions relating to specific criminal offences including, but not limited to, bribery, corruption, conspiracy, terrorism, fraud and money laundering, or if you have been the subject of a binding legal decision which found a breach of legal obligations to pay tax or social security obligations.

- Within the past five years, have you or your organisation (or any member of your proposed consortium, if applicable)- if you are trading as a company - Directors or Partner or any other person who has powers of representation, decision or control been convicted of any of the following offences? Individual Consultants – please complete the table to the best of your knowledge.

| Please Mark ‘X’ In the Relevant Box | Yes | No |
| --- | --- | --- |
| - Conspiracy as defined by the legislative or judicial bodies in your jurisdiction. | s | x |
| - Corruption as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - Bribery as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - The offence of cheating the Revenue as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - The offence of conspiracy to defraud as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - Fraud as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - Theft as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - Fraudulent trading as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - Fraudulent evasion as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - Destroying, defacing or concealing of documents or procuring the execution of a valuable security as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - The possession of articles for use in frauds as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - Any offence considered to be Counter Terrorism as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - Money laundering as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - Any Sexual Offences as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - Drug trafficking as defined by the legislative or judicial bodies in your jurisdiction. |  |  |

- Within the past three years, please indicate if any of the following situations have applied, or currently apply, to you (if an Individual Consultant) or your organisation.

| Please Mark ‘X’ In the Relevant Box | Yes | No |
| --- | --- | --- |
| - You/your organisation is bankrupt or is the subject of insolvency or winding-up proceedings, where your assets are being administered by a liquidator or by the court, where it is in an arrangement with creditors, where its business activities are suspended or it is in any analogous situation arising from a similar procedure under the laws and regulations of any State; |  |  |
| - You/your organisation is guilty of grave professional misconduct, which renders its integrity questionable; |  |  |
| - You/your organisation has entered into agreements with other economic operators aimed at distorting competition; |  |  |
| - the prior involvement of you/your organisation in the preparation of the procurement procedure has resulted in a distortion of competition; |  |  |
| - you/your organisation has shown significant or persistent deficiencies in the performance of a substantive requirement under a prior contract with a contracting entity, or a prior concession contract, which led to early termination of that prior contract, damages or other comparable sanctions. |  |  |

- Employment and Human Rights

For organisations working outside of the UK please refer to equivalent legislation in the country that you are located. Please delete ‘Yes’ / ‘No’ as applicable.

| (a) | In the last three years, has any finding of unlawful discrimination been made against you/your organisation by an Employment Tribunal, an Employment Appeal Tribunal or any other court (or in comparable proceedings in any jurisdiction other than the UK)? | Yes/No |
| --- | --- | --- |
| (b) | In the last three years, have you or has your organisation had a complaint upheld following an investigation by the Equality and Human Rights Commission or its predecessors (or a comparable body in any jurisdiction other than the UK), on grounds or alleged unlawful discrimination? If you have answered “yes” to one or both of the questions, please provide, as a separate Appendix, a summary of the nature of the investigation and an explanation of the outcome of the investigation to date. If the investigation upheld the complaint against your organisation, please use the Appendix to explain what action (if any) you have taken to prevent unlawful discrimination from reoccurring. You may be excluded if you are unable to demonstrate to The Secretariat’s satisfaction that appropriate remedial action has been taken to prevent similar unlawful discrimination reoccurring. | Yes/No |
| (c) | If you use sub-contractors, do you have processes in place to check whether any of the above circumstances apply to these other organisations? | Yes/No/ NA |

- Environmental Legislation

For organisations working outside of the UK please refer to equivalent legislation in the country that you are located. Please delete ‘Yes’ / ‘No’ as applicable.

| (a) | Have you or your organisation been convicted of breaching environmental legislation, or had any notice served upon it, in the last three years by any environmental regulator or authority (including local authority)? If your answer to this question is “Yes”, please provide details in a separate Appendix of the conviction or notice and details of any remedial action or changes you have made as a result of conviction or notices served. The Secretariat will not select bidders that have been prosecuted or served notice under environmental legislation in the last 3 years, unless The Commonwealth is satisfied that appropriate remedial action has been taken to prevent future occurrences/breaches. | Yes/No |
| --- | --- | --- |
| (b) | If you use sub-contractors, do you have processes in place to check whether any of these organisations have been convicted or had a notice served upon them for infringement of environmental legislation? | Yes/No/ NA |

- Health and Safety legislation

For individuals/organisations working outside of the UK please refer to equivalent legislation in the country that you are registered in and/or located. Please delete ‘Yes’ / ‘No’ as applicable.

| (a) | Please self-certify that your organisation has a Health and Safety Policy that complies with current legislative requirements. | Yes/No/NA (individual consultant) |
| --- | --- | --- |
| (b) | Has your organisation or any of its Directors or Executive Officers been in receipt of enforcement/remedial orders in relation to the Health and Safety Executive (or equivalent body) in the last 3 years? If your answer to this question was “Yes”, please provide details in a separate Appendix of any enforcement/remedial orders served and give details of any remedial action or changes to procedures you have made as a result. The Secretariat will exclude bidder(s) that have been in receipt of enforcement/remedial action orders unless the bidder(s) can demonstrate to The Secretariat’s satisfaction that appropriate remedial action has been taken to prevent future occurrences or breaches. | Yes/No/NA (individual consultant) |
| (c) | If you use sub-contractors, do you have processes in place to check whether any of the above circumstances apply to these other organisations? | Yes/No/ NA (individual consultant) |

- Insurance requirements (for information)

Does the Consultant (whether an Individual or Company) have insurances (as may be necessary or relevant by the subject matter of the contract specified in the ToR in this RFQ), currently in place, for the business activities they are proposing to carry out?

YES

NO

If Yes, please state the type of insurance and level of insurance held:

| Area | Does the Consultant/supplier have insurances in place? | Level of cover expected | Level of cover currently held |
| --- | --- | --- | --- |
| e.g. Public liability | Yes/No/NA | £10m |  |
| e.g. Employer’s liability | Yes/No/NA | £5m |  |
| e.g. Professional Indemnity | Yes/No/NA | £1m |  |
| e.g. Data Protection Liability (for relevant projects only, where the supplier will be handling/processing personal data on behalf of the Secretariat) | Yes/No/NA | See below |  |

Please note that the Individual Consultant will not be excluded from the tender process if the answer is ‘No’. However, it is industry best practice for consultants to ensure they have suitable insurances in place for the work they are proposing to undertake.

Please note that the insurance cover detailed above should be in place before activities commence in pursuance of the services required (if successful) and will not be considered as part of the costs under the contract between the Secretariat and the selected consultant.

- Terms and Conditions/Code of Ethics/Corporate Policies

Please delete ‘Yes’ / ‘No’ as applicable.

| (a) | Please confirm that you (if an Individual Consultant)/your organisation agrees to the Commonwealth Secretariat’s: 1. Secretariat’s standard terms and conditions for below £30,000 total contract value can be found at: https://thecommonwealth.org/terms-and-conditions 2. Secretariat’s Code of Ethics and Safeguarding Policy at: https://thecommonwealth.org/corporate-policies and 3. Secretariat’s Corporate policies applicable to Consultant/suppliers and as published from time to time on the following web page: https://thecommonwealth.org/corporate-policies ………………………………………………………………………………………………………………….. If you do not agree to abide by the above, please state reasons and/or changes requested as part of your bid: | Yes/No |
| --- | --- | --- |

- Legal comments table

By submitting a response, the bidder is agreeing to be bound by the terms of this RFQ and the Contract save as in relation to those areas of the Contract specifically highlighted below.  As such, if the terms & conditions of the Commonwealth Secretariat Terms and Conditions | Commonwealth (thecommonwealth.org) renders proposals in the bidder’s response unworkable, the bidder must submit full details of the unworkable/unacceptable provisions within the relevant Standard Terms and Conditions (Consultancy or Goods and Services) by completing the Legal Comments Table below.

| Clause/Paragraph /Schedule | Summary of Issue | Suggested Revisions |
| --- | --- | --- |

Part 3 – Technical Questionnaire

The following scoring mechanism will be used to score each question in this section:

| Using a 0 – 5 scoring system: |  |
| --- | --- |
| 0 | Unacceptable Response – No information provided or response does not address the requirement. |
| 1 | Poor response – The response contains material omissions and / or is supported by limited evidence / examples. Concerns that the organisation does not have the potential to deliver / that they have failed to meet a reasonable standard. |
| 2 | Fair response – There is adequate detail / supporting examples giving a reasonable level of confidence in the Tenderer’s experience and ability. The Tenderer appears to have the potential to deliver as required / has met a reasonable standard and there are only minor concerns about the Tenderer’s experience |
| 3 | Good Response – The level of detail / supporting examples gives a high level of confidence in the Tenderer’s experience and ability. The Tenderer clearly has the potential to deliver and / or has clearly met an acceptable standard. |
| 4 | Excellent Response – A comprehensive well evidenced submission, clearly demonstrating expertise and knowledge incorporating some value-added benefits attributes & other points of innovation. The bid is deemed to offer little risk and fully captures the understanding of the steps involved to deliver aspects of the service which can be related to the question posed, giving a high level of confidence in the Tenderer’s experience and ability. |
| 5 | Exceptional Response – A comprehensive and exceptionally evidenced submission that substantially exceeds the expectations of the requirement and offers significant additional benefits. Submission clearly demonstrates exceptional expertise and knowledge incorporating value added benefits/ & other points of innovation. The bid is deemed to offer well identified risks and a mitigation of these put forward and fully captures the understanding of the steps involved to deliver all the aspects of the service and is directly relatable to the question posed, giving an exceptionally high level of confidence in the Tenderer’s experience and ability. |

- The technical questions below are worth 100% of the total score. The individual question weightings are set out in the weighting column.

- The following formula will be applied for each question:

  - Points Scored ÷ Points Available × % weighting

  - The scores for each of the questions will be added to give a total Technical/Quality Score

- Unanswered questions or sections that are left blank shall be awarded a 0.

Please answer all questions in the spaces provided. Please do not attach documents or appendices.

| Question No. | Question | Weighting |
| --- | --- | --- |
| 1 | Lead Consultant: Does the lead consultant possess a postgraduate degree (Master’s) in Gender Studies, Climate Change, Environmental Studies and/or related discipline? | 6% |
| Insert your answer here |  |  |
| 2 | Lead Consultant: Does the lead consultant possess any additional qualifications (relevant to the position)? | 4% |
| Insert your answer here |  |  |
| 3 | Lead Consultant: Does the lead consultant have strong communication skills – fluency in written and spoken English? | 5% |
| Insert your answer here |  |  |
| 4 | Does the firm/consultant have 7-15 years of relevant work experience in the areas of gender equality and climate change, preferably in an international development context? | 10% |
| Insert your answer here |  |  |
| 5 | Does the firm/consultant have experience in working with government/Commonwealth and international institutions on gender equality and climate change, preferably in an international development context? | 10% |
| Insert your answer here |  |  |
| 6 | Does the firm/consultant have strong expertise in gender-responsive climate policy, UNFCCC processes, and NDC development? | 25% |
| Insert your answer here |  |  |
| 7 | Does the firm/consultant have expertise in gender analysis, and substantial experience in considering the gender aspects of climate change? | 25% |
| Insert your answer here |  |  |
| 8 | Does the firm/consultant have excellent analytical and writing skills? | 15% |
| Insert your answer here |  |  |

Part 4 – Pricing

If there is a VAT element - for UK VAT registered consultants only – this must be itemised in the total quote received/agreed by the Secretariat and the consultants must submit a UK VAT registration certificate to the Secretariat when invoicing.

Consultants are expected (within their financial proposal) to provide a full breakdown of the number of experts/number of days (total and per expert) needed to complete the assignment.

Consultants are to give an indication as to which Band each Consultant’s fee falls within in the Secretariat’s Technical Assistance Consultants: Corporate Fee Band Table (see Annex 1). Include CVs of all staff proposed. Please note that the maximum daily fee rates can not normally exceed £700.

| Consultant’s Name/Role/Band – refer to Annex 1 Technical Assistance Consultants: Corporate Fee Band Table Experts name/role |  | Day Rate (including all taxes) | No of Days | Total (including all taxes) GBP |
| --- | --- | --- | --- | --- |
| Total |  |  |  |  |

If expenses are applicable for this assignment, insert the following table:

| Expenses: |  |  |  |
| --- | --- | --- | --- |
| Per diem (to be in line with Secretariat’s policies on travel and per diem rates) |  |  |  |
| Travel (to be in line with Secretariat’s travel policies) |  |  |  |
| Other (please list) |  |  |  |
| Total in GBP |  |  |  |

Annex 1 – Secretariat’s Technical Assistance Consultants: Corporate Fee Band Table

The consultancy fee rate range associated with a particular level of assignment may be based on the following:

- Knowledge, qualifications, experience, and skills required.

- Level of work in terms of responsibilities and complexity of the assignment.

- Degree of specialization required by the assignment.

| Band | Per Day (GBP) | Comments and Guidelines |
| --- | --- | --- |
| A* | 700+ | - Extensive achievement in their specialist field, in which they are nationally or internationally renowned. Extensive experience of leading or directing major, complex and business-critical projects, bringing genuine strategic insight, understanding the range of services to be delivered. In depth knowledge of the international sector/specialist field and of current policy and political issues affecting it. - Contributions to the accomplishment of a crucial programme or service or functional area of a broad scope, involving high complexity and impact. - Providing functional leadership and expert advice. - Preparing intricate and complex technical papers to working groups. - Undertaking the drafting of reports or proposals for projects of a large scale or a broad scope. - Large-scale programmatic and operational activities involving large commitments of staff and funds. - Rare specialization - Industry equivalent level: Partner/Managing Director |
| B | 500-699 | - Substantial experience in their specialist field and operating multiple major consultancy assignments achieving specific revenue and income objectives to agreed outcomes. - Within this category the person is expected to have significant, proven, industry recognised experience. - Expected to develop new approaches, techniques, or policies and/or design guidelines, standard operating procedures. - Providing technical support; leading group dynamics; and undertaking report drafting or project-wide proposals. - Industry equivalent level: Principal/Senior Consultant |
| C | 350 - 499 | - Demonstrable experience and relevant exposure in a range of projects in a specialist field. - Evidence of client facing experience and relationship management. - Support for planning and monitoring budgets and services to wider consultancy projects; and experience of proposal preparation. - Industry equivalent level: Consultant |
| D | 300-349 | - Specialized degree or training and - Several years of relevant experience - Industry equivalent level: Junior Consultant |
| E | £100 - £299 | - This level is established for the engagement of support services not available in the Secretariat related to projects or technical tasks of a narrow scope for which limited technical skills or experience are required. - Industry equivalent level: Project Support |

*Rates above Band A must include appropriate justification in respect of the tasks involved, complexity of the assignment, number of workdays involved, duration/period and specific task deliverables and must, internally within the Secretariat, be referred to the DSG, ASG or Senior Director for review and approval ahead of any contract being awarded.

https://thecommonwealth.org/corporate-policies

https://thecommonwealth.org/corporate-policies

This will go some way to mitigate against bidders selecting the references that are likely to be more favorable and will assist in providing a more realistic reflection of performance.

Where contracts involve significant data processing, data protection cap needs to be determined on a case-by-case basis. For low-cost contracts that involve little (emails only) or no data processing, the liability is capped at 1.5 times of the contract value.