COMMONWEALTH SECRETARIAT

MARLBOROUGH HOUSE, PALL MALL, LONDON SW1Y 5HX

IN STRICT COMMERCIAL CONFIDENCE

Request for Quotations (RFQ)

For the provision of consultancy to Design and Deliver Judicial Training for the Nigeria Joint Case Team on Cybercrime (JCTC).

| Secretariat Reference Number: | GPD/ROL/CC/ATE2387/09/2026 |
| --- | --- |
| Return Date: | 5 PM ON 24 SEPTEMBER 2026 |
| Estimated Contract Award: | OCTOBER 2026 |

Contents

1.	Introduction	3

2.	Purpose	3

3.	Instructions to Bidders	3

4.	Evaluation Weightings	3

5.	Quote Timeline	4

6.	Information for Bidders	4

7.	Terms of Reference	6

Part 1 – Bidder Details	12

Part 2 - Suitability Assessment Questions	13

Part 3 – Technical Questionnaire	19

Part 4 – Pricing	21

Annex 1 - Secretariat’s Technical Assistance Consultants: Corporate Fee Band Table 	      22

# Introduction

The Commonwealth Secretariat (The Secretariat) is an international organisation established by Agreed Memorandum, which is given privileges and immunities under the domestic law of the United Kingdom by the Commonwealth Secretariat Act 1966 (as amended by the International Organisations Act 2005). Under this legislation, the Secretariat is not subject to UK jurisdiction and enforcement.

This status has an impact on some of our standard terms and conditions. In particular, we draw your attention to our dispute resolution clause, which refers disputes to the exclusive jurisdiction of the Commonwealth Secretariat Arbitration Tribunal (CSAT). The 8 members of the Tribunal are selected by the Board of Governors and come from Commonwealth member countries. Information about CSAT, including its governing statute and procedure are available on its website at http://thecommonwealth.org/tribunal.

The Secretariat implements decisions agreed by 56 Heads of Government and Ministers through advocacy, consensus–building, information sharing, analysis, technical assistance, capacity-building, and advice on policy development.

# Purpose

The purpose of this request for a quote (RFQ) is to find and appoint a suitable consultant for the design and deliver Judicial Training for the Nigeria Joint Case Team on Cybercrime (JCTC). The appointed consultant shall be awarded a contract that will be effective for up to six (6)months.

See Specification of Requirements/Terms of Reference in Section 7 for details on the services required.

# Instructions to Bidders

This is a one-stage RFQ process with a written submission to this RFQ followed by bidder clarifications, if required. Bidders will be scored following the first stage and if required bidders may be asked to attend a clarification of their Quote meeting.

Bidders must submit all documents as set out in Part1 – Part 5 ‘Quote’ no later than the return date of 5PM GMT on 24th September 2026. The quote documents are to be returned to the following email address: n.amobi@commonwealth.int copying in  cybercrime@commonwealth.int

Following all stages of the Quote process, the quote received that is deemed to offer the best overall value to the Commonwealth Secretariat, shall be awarded the contract based on the notified evaluation weightings:

# Evaluation Weightings

Quality 80%

Price 20%

The lowest price bid shall be awarded the full points, all other bids shall be awarded a percentage from the benchmark. E.g. (lowest price/other bid)*weighting = Score.

# Quote Timeline

Please note that the following timeline is an estimate and may change at short notice.

| Activity | Date |
| --- | --- |
| Request for quote (RFQ) issued | 10 September 2026 |
| Clarification questions to be submitted by bidders by | 16 September 2026 |
| Secretariat’s response to (anonymised) clarification questions will be circulated to all in writing by | 18 September 2026 |
| Quotes submission closing date | 24 September 2026 |
| Contract Start Date | October 2026 |

# Information for Bidders

- Unless indicated otherwise, all prices should be quoted in Pounds Sterling.  Prices quoted for Technical Assistance Consultancy should include taxes and should be submitted on an all-inclusive fixed basis, providing a breakdown of day rates per named Consultant mapped against the Secretariat’s TAP Consultants: Corporate Fee Band Table (annexed to this RFQ)

- The bidder must ensure that they have all the information required for the preparation of the Quote submission and that they are satisfied with the correct interpretation of terminology used in this documentation. The bidder must also ensure that they are fully conversant with the nature and extent of the obligations should the Quote be accepted.

- Quotes are to be valid for a minimum of 30 days from the closing date for the submission of the Quotes.

- The Commonwealth Secretariat reserves the right to cancel the RFQ at any time during the process and not to award a contract as a result of this procurement.

- Bidders shall bear all costs in completing a quotation submission.

- Bidders shall not disclose details of the RFQ to third parties without prior agreement from an authorised officer of the Commonwealth Secretariat.

- All clarification queries must be submitted by 5 PM GMT 16 September 2026 to n.amobi@commonwealth.int, copying   cybercrime@commonwealth.int;

- Bidders are required to submit transparent pricing with no hidden costs or charges.

- The Secretariat will carry out an evaluation of the quotes using the weighted criteria method as described. Following the evaluation stage(s), the Secretariat will select a preferred bidder, which will be taken forward to contract award. The Secretariat reserves the right to appoint a reserve preferred bidder, which it could then take forward to contract award if contract negotiations with the preferred bidder are unsuccessful.

By taking part in this request for quotes, all bidders commit to the following:

- Bidders confirm that by submitting a quote they agree to abide by the Secretariat’s Code of  Ethics and relevant Corporate policies as published from time to time on the following web page:

https://thecommonwealth.org/corporate-policies

- Bidders certify that they have not canvassed or solicited any officer or employee of the Secretariat in connection with this Quote submission and that no person employed or acting on behalf of the bidder has done any such act.

- The CSAT shall have exclusive jurisdiction to settle any dispute or claim that arises out of or in connection with this Procurement (including non-contractual disputes or claims).

- Compliance with policies: The Secretariat has a zero-tolerance approach towards sexual exploitation, abuse and harassment. The bidder must familiarise itself with the Secretariat’s policies available at https://thecommonwealth.org/corporate-policies.  Particularly with reference to the Anti- Bribery and the Safeguarding Policy, the bidder must understand the obligations imposed on Suppliers/Consultants and their personnel and sub-contractors including having robust procedures to detect and report any wrongdoing or concerns. Adherence to the Secretariat policies is mandatory and if awarded a contract, the Supplier/Consultant will be required to ensure continued compliance with the policies for the duration of the contract.

# Terms of reference (ToR)

Terms of Reference

Title: 	Consultancy to design and deliver judicial training for the Federal High Court Judges designated to the Nigeria Joint Case Team on Cybercrime (JCTC).

Organisational Section/Unit: 	Governance and Peace Directorate, Commonwealth Secretariat

Duty Station:	Home Based/Field Based

Proposed period: 			October 2026- February 2027

Actual work time: 			up to 40 workdays within the proposed period

- INTRODUCTION

Cybercrime is among Nigeria's most significant socio-economic and security threats, with impacts that extend directly to many Commonwealth countries, including the United Kingdom, through shared ties in trade, finance, migration and digital infrastructure. Nigeria has responded by anchoring enforcement in the Cybercrime (Prohibition, Prevention, etc.) Act 2015 (as amended in 2024) and by establishing the Joint Case Team on Cybercrime (JCTC), an integrated, multi-agency platform that brings together investigators, prosecutors, financial intelligence agencies, cybersecurity authorities and designated Federal High Court judges.

Adjudication remains the decisive test of any cybercrime case. Familiarity with cyber-specific law and electronic evidence varies considerably among the judges designated to the JCTC, and this gap can cause even well-investigated and well-prosecuted cases to fail at trial. The judges themselves identified this gap during a 2025 Commonwealth Secretariat-delivered symposium and issued a clear, judge-led mandate for further specialist training, expanded judicial numbers and improved case-management practices.

With FCDO funding, the Commonwealth Secretariat is implementing a follow-on programme to respond to that mandate: an intensive, practice-oriented capacity-building programme for Federal High Court judges designated to the JCTC, delivered in four phases over 7 months, and designed to cascade specialist expertise across Nigeria's federal judiciary through a structured, train-the-trainer mentorship model.

This document sets out the terms of reference to guide the work of the consultant(s) engaged by the Commonwealth Secretariat (“the Secretariat”) to design high-quality training materials and deliver training to the JCTC-designated judges.

- ASSIGNMENT

The Commonwealth Secretariat is seeking to engage a qualified individual consultant, or a small team led by a lead consultant, to design and deliver specialist judicial training on cybercrime adjudication and electronic evidence for the JCTC-designated judges, and to support the development of a sustainable, institutionalised train-the-trainer and mentorship model for Nigeria's Federal High Court.

Under the overall supervision of the Project Lead or their delegate, the consultant will be required to:

- Build and strengthen the capacity of the designated JCTC judges to adjudicate complex cybercrime and electronic-evidence cases in line with international standards.

- Design and deliver a practice-oriented curriculum covering cybercrime typologies, artificial intelligence, cryptocurrency-enabled crime, cross-border cooperation and mutual legal assistance (MLA), technology-facilitated gender-based violence (TFGBV), hybrid and state-linked cyber threats, and judicial ethics in technologically complex proceedings.

- Design and facilitate full-scale mock trials and multidisciplinary courtroom simulations, enabling judges to practise evidential rulings, expert witness management, case management and judgment writing under realistic conditions.

- Support the development of a sustainable train-the-trainer and peer-mentorship model to equip participating judges to mentor fellow Federal High Court judges and cascade expertise nationally.

- Produce reusable, high-quality knowledge products including judicial guidance notes, a participant resource manual and digital learning content suitable for integration into the National Judicial Institute's (NJI) continuing judicial education curriculum.

- Contribute to the programme's monitoring, evaluation and learning (MEL) framework, including design and administration of pre- and post-training assessments.

- Work collaboratively with staff of the Commonwealth Secretariat and other key stakeholders.

- SCOPE OF WORK

The consultant will work in close coordination with the Commonwealth Secretariat's Cyber Programme team, the JCTC Secretariat, the Federal Ministry of Justice, the National Judicial Institute (NJI) and the British High Commission, Abuja, to deliver the training and simulation components of the programme's four work packages, focusing principally on Work Package One (judicial capacity development), Work Package Three (mock trials and simulation) and Work Package Four (sustainability and mentorship). Specific tasks include:

3.1 Curriculum design and preparation

- Review the 2025 symposium report, including the judges' recommendations, and relevant Nigerian legislation (including the Cybercrime (Prohibition, Prevention, etc.) Act 2015, as amended in 2024) to ensure the curriculum is directly relevant and locally grounded.

- Review regional and international instruments on cybercrime, such as the Malabo Convention, the UN Convention on Cybercrime, and the Budapest Convention on Cybercrime.

- Design a Judicial Cybercrime Training Curriculum, a participant resource manual, including facilitator guides, lesson plans and practical exercises for a 3-day foundational block and a 2–4-day advanced block.

- Develop pre- and post-training assessment tools to measure changes in judicial knowledge and confidence.

  - Delivery of core intensive training (Phase 1)

- Facilitate the foundational and advanced training blocks for the designated judges, covering cybercrime typologies; AI-enabled criminality; cyber-enabled crime; and cross-border cooperation and MLA; TFGBV; hybrid and state-linked threats; human rights and judicial safeguards; and judicial reasoning in technically complex cases.

  - Mock trials and courtroom simulations (Phase 3)

- Design realistic case scenarios, digital evidence bundles, witness statements and expert reports for full-scale, multidisciplinary mock trials involving investigators, prosecutors, defence counsel and digital forensic experts drawn from the wider JCTC.

- Facilitate mock trial sessions, enabling judges to practise admissibility rulings, expert witness management and judgment writing, and provide structured feedback.

  - Sustainability, mentorship and consolidation (Phase 4)

- Support the design of a Judicial Mentorship Framework, including mentor guidance and a roadmap for cascading expertise across the Federal High Court.

- Prepare participating judges for their role as trainers/mentors through structured train-the-trainer sessions.

- Draft Judicial Guidance Notes on priority adjudication topics, a Cybercrime Case Compendium, and a Participant Resource Manual.

- Working with the Commonwealth Cyber team to prepare a consolidated Phase 4 report documenting the programme's outcomes, lessons learned, emerging good practices and recommendations, including priorities for sustaining and further strengthening judicial capacity on cybercrime and electronic evidence.

- DELIVERABLES AND OUTPUTS

| Deliverables | Timeline |
| --- | --- |
| - Inception note confirming methodology, detailed session plans and training/assessment tools for Phase 1 (Core Intensive Training), aligned to the JCTC judges' mandate and prior symposium recommendations | Within 2 weeks of signing the contract |
| - Finalised Judicial Cybercrime Training Curriculum (modules, facilitator guides, lesson plans, practical exercises) for the foundational and advanced training blocks | Prior to Phase 1 delivery |
| - Delivery of Phase 1 Core Intensive Training (foundational block, 3 days, and advanced block, 2–4 days) to the designated judges, including pre- and post-training assessments | November 2026 |
| - Design and delivery of Phase 3 mock trials and multidisciplinary courtroom simulations, including case scenarios, digital evidence bundles and evaluation tools | November 2026 |
| - Judicial Guidance Notes on priority adjudication topics (admissibility of electronic evidence; expert witness management; judicial case management; human rights and due process) | October 2026- February 2027 |
| - Train-the-trainer materials to prepare beneficiary judges to mentor peers across the Federal High Court | October 2026-February 2027 |
| - Participant Resource Manual and reusable digital learning content for integration into the National Judicial Institute's curriculum | October 2026- February 2027 |

- DURATION AND LEVEL OF EFFORT

- The assignment is expected to run for approximately 5 months within the programme's overall 7-month delivery period.

- The level of effort is estimated at 40 consultant days, inclusive of preparation, delivery and reporting.

- Delivery will combine in-person sessions in Abuja or Lagos (or another agreed Nigerian venue) with remote work for curriculum development, judicial guidance notes, materials preparation and reporting.

- INDICATORS TO EVALUATE THE CONSULTANT’S PERFORMANCE

Potential candidates shall be evaluated based on competency and cost. In addition, all outputs will be assessed using the following indicators.

| Deliverables | Indicators |
| --- | --- |
| a, b, c, d, e, f, g, and i | - Quality of data and analysis (accuracy, coherence, reliability, and relevance) - Technical excellence |
| a, b, c, d, e, f, g, and i | - All comments from the Secretariat appropriately reflected - Excellent writing skills - Political nuances fully considered - Technical excellence. |

- IDEAL PROFILE OF CANDIDATE

Education and Experience

The consultant (or lead consultant, where a team is proposed) should hold or demonstrate:

- An advanced degree in law, public policy, criminal justice, or a closely related field.

- Substantial experience in designing and delivering judicial or legal-professional training on cybercrime or related technology-law fields, ideally within Commonwealth jurisdictions.

- Minimum of ten (10) years of relevant experience supporting the strengthening of criminal justice systems, and/or proven research, policy, or teaching experience in critical areas of political, governance, social, human rights, or criminal law.

- Knowledge of curriculum development.

- Demonstrated experience providing legal and policy advice.

- Familiarity with Nigeria's legal and institutional framework for cybercrime, or comparable experience in another African or Commonwealth common-law jurisdiction.

- Experience in developing training curricula, facilitator guides and bench/judicial guidance materials suitable for institutional adoption (e.g. by a national judicial institute or training college).

- Sound understanding of gender-responsive and inclusive training approaches, including in relation to technology-facilitated gender-based violence.

- Excellent facilitation, communication and report-writing skills in English.

- Prior experience working with the Commonwealth Secretariat, FCDO-funded programmes, or international justice-sector capacity-building initiatives is an advantage.

- Experience in judicial training or presenting to high-level audiences, including judicial officials.

- LANGUAGES

- Excellent English writing and communication skills are required.

- KNOWLEDGE, SKILLS AND ABILITIES

- Solid understanding and knowledge of cybercrime and electronic evidence.

- Strong research design and content development skills, including the capacity to prepare accurate, relevant, reliable and analytical legal and policy documents.

- Highly developed communication skills, including the ability to draft/edit texts and articulate ideas in a clear, concise style to a variety of audiences, as well as facilitation skills

- Ability to work with high accuracy and attention to quality and detail on complex assignments.

- Sound organisational and planning skills, including the proven ability to meet strict deadlines.

- Flexibility to adapt to any subsequent changes in the terms of reference.

- Strong interpersonal and communication skills and ability to work constructively with several internal and external stakeholders.

- Openness to change and ability to receive/integrate feedback.

- Good team player, positive attitude, flexible and comfortable working in multi-cultural settings.

- ADMINISTRATIVE ARRANGEMENTS

The tasks associated with this ToR are expected to be completed over a contract period from October 2026 to March 2027.

The Consultant will receive a fee of up to £20,000 (inclusive of VAT and all other applicable taxes, fees and charges) for the consultancy services, payable upon the satisfactory completion of the agreed milestones.  The Consultant shall, however, be responsible for all travel costs associated with the assignment, including international and domestic transportation.

The Consultant will report to the Commonwealth Secretariat's designated Project Lead for the Commonwealth Cyber Programme.

- EVALUATION CRITERIA

The Technical Questionnaire Quotes will be assessed based on the evaluation criteria outlined in this document (see skills and experience required and the weightings apportioned to quality/price above in this Terms of reference/RFQ).

Part 1 Bidder’s details are for information only.

Part 2 - Suitability Assessment Questions will be assessed on a Pass/Fail basis.

- PAYMENTS

Payments will be made upon milestone completion and 30 days upon receipt of the Secretariat’s written approval of all agreed deliverables, the submission of a compliant invoice and any other supporting documents as may be required by the Secretariat. All invoices are to be sent to the contract manager at n.amobi@commonwealth.int copying cybercrime@commonwealth.int

Quote Submission Documents (ref GPD/ROL/CC/ATE2387/09/2026)

Note - Bidders must complete and return all Quote submission documents below:

Part 1 – Bidder Details

Part 2 – Suitability Assessment Questions

Part 3 – Technical Questionnaire

Part 4 – Pricing

Part 1 – Bidder Details (for information)

Please provide details of your registered offices, legal status, and date of incorporation.

| Individual/ Company and/or Trading Name |  |  |  |  | Company/Sole Trader Registration Number |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Company Address |  |  |  |  | Date of incorporation |  |  |  |  |
| Post Code |  |  |  |  |  |  |  |  |  |
| Contact Name |  |  |  |  | Job Title |  |  |  |  |
| Telephone |  |  |  |  | Email |  |  |  |  |
| In the event of utilising a third party, on your behalf for any part of the services, please provide the full details of the secondary consultant/supplier: |  |  |  |  |  |  |  |  |  |
| Company Name |  |  |  |  | Duration of working relationship, |  |  |  |  |
| Company Address |  |  |  |  | Reason for use |  |  |  |  |
| Post Code |  |  |  |  |  |  |  |  |  |
| In line with the Secretariat’s Procurement Code of EthicsThe Secretariat works to encourage SMEs to apply for relevant tenders and is committed to monitoring the environmental awareness of our consultants, suppliers and partners, with a view (where relevant to the subject matter of the contract) to doing business only with ISO 14001 Environmental Management or ISO 50001 Energy Management accredited organisations. |  |  |  |  |  |  |  |  |  |
| Is the Consultant classified as a Micro or Small Medium Enterprise (SME)?; Yes/No. Is the Consultant an ISO14001 or ISO 50001 (Energy Management) accredited organisation?; Yes/No. UK VAT Declaration For UK Registered consultant: Is the bidder registered for Value Added Tax (VAT)? [Y/N] If Yes, please include VAT registration number [insert] and provide a copy of your VAT registration certificate as part of your response. Annual Turnover check: In line with the Secretariat’s Procurement Code of Ethics, the Secretariat expects for its consultant/suppliers to have a turnover that is, as a minimum, twice the value of the contract they are applying for. Please state the following: |
|  | Annual |  | Previous Year |  |  |  |  | Year 2 |  |
|  | Turnover: |  | £ |  |  |  |  | £ |  |
| Or |  |  |  |  |  |  |  |  |  |
| For individual consultants, please confirm that your annual turnover is twice the value of the Contract you are applying for: YES Please note, the successful bidder (if a company and not an Individual) may also be checked for their Equifax Financial Credit Score. Should the bidder (if a company) fail the commercial credit score check, the Secretariat will be entitled to commence negotiations with the second preferred bidder subject to that bidder (if a Company) having passed the Equifax Credit Score and so forth. Please provide the contact details of two reference clients. A minimum of two references will be collected from previous clients (excluding the Secretariat) from projects carried out in (max) last 18 months. Please provide references from similar international organisations or public sector bodies or equivalent if possible. One of the references should relate to the most recent contract you/your company has fulfilled. If possible, additionally, supply a list of potential references from which the Secretariat can select the referees they wish to contact. The referees will not be contacted until the final stage of the Quote process. |
|  |  | Reference 1 |  |  |  | Reference 2 |  |  |  |
| Company Name |  |  |  |  |  |  |  |  |  |
| Company Address |  |  |  |  |  |  |  |  |  |
| Post Code |  |  |  |  |  |  |  |  |  |
| Referees name |  |  |  |  |  |  |  |  |  |
| Referee Telephone |  |  |  |  |  |  |  |  |  |
| Referee Email |  |  |  |  |  |  |  |  |  |

Part 2 - Suitability Assessment Questions (pass/fail)

Grounds for Exclusion

You will be excluded from the Quote process if there is evidence of convictions relating to specific criminal offences including, but not limited to, bribery, corruption, conspiracy, terrorism, fraud and money laundering, or if you have been the subject of a binding legal decision which found a breach of legal obligations to pay tax or social security obligations.

- Within the past five years, have you or your organisation (or any member of your proposed consortium, if applicable)- if you are trading as a company - Directors or Partner or any other person who has powers of representation, decision or control been convicted of any of the following offences? Individual Consultants – please complete the table to the best of your knowledge.

| Please Mark ‘X’ In the Relevant Box | Yes | No |
| --- | --- | --- |
| - Conspiracy as defined by the legislative or judicial bodies in your jurisdiction. | s | x |
| - Corruption as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - Bribery as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - The offence of cheating the Revenue as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - The offence of conspiracy to defraud as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - Fraud as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - Theft as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - Fraudulent trading as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - Fraudulent evasion as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - Destroying, defacing or concealing of documents or procuring the execution of a valuable security as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - The possession of articles for use in frauds as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - Any offence considered to be Counter Terrorism as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - Money laundering as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - Any Sexual Offences as defined by the legislative or judicial bodies in your jurisdiction. |  |  |
| - Drug trafficking as defined by the legislative or judicial bodies in your jurisdiction. |  |  |

- Within the past three years, please indicate if any of the following situations have applied, or currently apply, to you (if an Individual Consultant) or your organisation.

| Please Mark ‘X’ In the Relevant Box | Yes | No |
| --- | --- | --- |
| - You/your organisation is bankrupt or is the subject of insolvency or winding-up proceedings, where your assets are being administered by a liquidator or by the court, where it is in an arrangement with creditors, where its business activities are suspended or it is in any analogous situation arising from a similar procedure under the laws and regulations of any State; |  |  |
| - You/your organisation is guilty of grave professional misconduct, which renders its integrity questionable; |  |  |
| - You/your organisation has entered into agreements with other economic operators aimed at distorting competition; |  |  |
| - the prior involvement of you/your organisation in the preparation of the procurement procedure has resulted in a distortion of competition; |  |  |
| - you/your organisation has shown significant or persistent deficiencies in the performance of a substantive requirement under a prior contract with a contracting entity, or a prior concession contract, which led to early termination of that prior contract, damages or other comparable sanctions. |  |  |

- Employment and Human Rights

For organisations working outside of the UK please refer to equivalent legislation in the country that you are located. Please delete ‘Yes’ / ‘No’ as applicable.

| (a) | In the last three years, has any finding of unlawful discrimination been made against you/your organisation by an Employment Tribunal, an Employment Appeal Tribunal or any other court (or in comparable proceedings in any jurisdiction other than the UK)? | Yes/No |
| --- | --- | --- |
| (b) | In the last three years, have you or has your organisation had a complaint upheld following an investigation by the Equality and Human Rights Commission or its predecessors (or a comparable body in any jurisdiction other than the UK), on grounds or alleged unlawful discrimination? If you have answered “yes” to one or both of the questions, please provide, as a separate Appendix, a summary of the nature of the investigation and an explanation of the outcome of the investigation to date. If the investigation upheld the complaint against your organisation, please use the Appendix to explain what action (if any) you have taken to prevent unlawful discrimination from reoccurring. You may be excluded if you are unable to demonstrate to The Secretariat’s satisfaction that appropriate remedial action has been taken to prevent similar unlawful discrimination reoccurring. | Yes/No |
| (c) | If you use sub-contractors, do you have processes in place to check whether any of the above circumstances apply to these other organisations? | Yes/No/ NA |

- Environmental Legislation

For organisations working outside of the UK please refer to equivalent legislation in the country that you are located. Please delete ‘Yes’ / ‘No’ as applicable.

| (a) | Have you or your organisation been convicted of breaching environmental legislation, or had any notice served upon it, in the last three years by any environmental regulator or authority (including local authority)? If your answer to this question is “Yes”, please provide details in a separate Appendix of the conviction or notice and details of any remedial action or changes you have made as a result of conviction or notices served. The Secretariat will not select bidders that have been prosecuted or served notice under environmental legislation in the last 3 years, unless The Commonwealth is satisfied that appropriate remedial action has been taken to prevent future occurrences/breaches. | Yes/No |
| --- | --- | --- |
| (b) | If you use sub-contractors, do you have processes in place to check whether any of these organisations have been convicted or had a notice served upon them for infringement of environmental legislation? | Yes/No/ NA |

- Health and Safety legislation

For individuals/organisations working outside of the UK please refer to equivalent legislation in the country that you are registered in and/or located. Please delete ‘Yes’ / ‘No’ as applicable.

| (a) | Please self-certify that your organisation has a Health and Safety Policy that complies with current legislative requirements. | Yes/No/NA (individual consultant) |
| --- | --- | --- |
| (b) | Has your organisation or any of its Directors or Executive Officers been in receipt of enforcement/remedial orders in relation to the Health and Safety Executive (or equivalent body) in the last 3 years? If your answer to this question was “Yes”, please provide details in a separate Appendix of any enforcement/remedial orders served and give details of any remedial action or changes to procedures you have made as a result. The Secretariat will exclude bidder(s) that have been in receipt of enforcement/remedial action orders unless the bidder(s) can demonstrate to The Secretariat’s satisfaction that appropriate remedial action has been taken to prevent future occurrences or breaches. | Yes/No/NA (individual consultant) |
| (c) | If you use sub-contractors, do you have processes in place to check whether any of the above circumstances apply to these other organisations? | Yes/No/ NA (individual consultant) |

- Insurance requirements (for information)

Does the Consultant (whether an Individual or Company) have insurances (as may be necessary or relevant by the subject matter of the contract specified in the ToR in this RFQ), currently in place, for the business activities they are proposing to carry out?

YES

NO

If Yes, please state the type of insurance and level of insurance held:

| Area | Does the Consultant/supplier have insurances in place? | Level of cover expected | Level of cover currently held |
| --- | --- | --- | --- |
| e.g. Public liability | Yes/No/NA | £10m |  |
| e.g. Employer’s liability | Yes/No/NA | £5m |  |
| e.g. Professional Indemnity | Yes/No/NA | £1m |  |
| e.g. Data Protection Liability (for relevant projects only, where the supplier will be handling/processing personal data on behalf of the Secretariat) | Yes/No/NA | See below |  |

Please note that the Individual Consultant will not be excluded from the tender process if the answer is ‘No’. However, it is industry best practice for consultants to ensure they have suitable insurances in place for the work they are proposing to undertake.

Please note that the insurance cover detailed above should be in place before activities commence in pursuance of the services required (if successful) and will not be considered as part of the costs under the contract between the Secretariat and the selected consultant.

- Terms and Conditions/Code of Ethics/Corporate Policies

Please delete ‘Yes’ / ‘No’ as applicable.

| (a) | Please confirm that you (if an Individual Consultant)/your organisation agrees to the Commonwealth Secretariat’s: 1. Secretariat’s standard terms and conditions for below £30,000 total contract value can be found at: https://thecommonwealth.org/terms-and-conditions 2. Secretariat’s Code of Ethics and Safeguarding Policy at: https://thecommonwealth.org/corporate-policies and 3. Secretariat’s Corporate policies applicable to Consultant/suppliers and as published from time to time on the following web page: https://thecommonwealth.org/corporate-policies ………………………………………………………………………………………………………………….. If you do not agree to abide by the above, please state reasons and/or changes requested as part of your bid: | Yes/No |
| --- | --- | --- |

- Legal comments table

By submitting a response, the bidder is agreeing to be bound by the terms of this RFQ and the Contract save as in relation to those areas of the Contract specifically highlighted below.  As such, if the terms & conditions of the Commonwealth Secretariat Terms and Conditions | Commonwealth (thecommonwealth.org) renders proposals in the bidder’s response unworkable, the bidder must submit full details of the unworkable/unacceptable provisions within the relevant Standard Terms and Conditions (Consultancy) by completing the Legal Comments Table below.

| Clause/Paragraph /Schedule | Summary of Issue | Suggested Revisions |
| --- | --- | --- |

Part 3 – Technical Questionnaire

The following scoring mechanism will be used to score each question in this section:

| Using a 0 – 5 scoring system: |  |
| --- | --- |
| 0 | Unacceptable Response – No information provided or response does not address the requirement. |
| 1 | Poor response – The response contains material omissions and / or is supported by limited evidence / examples. Concerns that the organisation does not have the potential to deliver / that they have failed to meet a reasonable standard. |
| 2 | Fair response – There is adequate detail / supporting examples giving a reasonable level of confidence in the Tenderer’s experience and ability. The Tenderer appears to have the potential to deliver as required / has met a reasonable standard and there are only minor concerns about the Tenderer’s experience |
| 3 | Good Response – The level of detail / supporting examples gives a high level of confidence in the Tenderer’s experience and ability. The Tenderer clearly has the potential to deliver and / or has clearly met an acceptable standard. |
| 4 | Excellent Response – A comprehensive, well-evidenced submission that clearly demonstrates expertise and knowledge, incorporating some value-added benefits, attributes & other points of innovation. The bid is deemed to pose little risk and fully captures an understanding of the steps involved in delivering aspects of the service relevant to the question posed, giving a high level of confidence in the Tenderer’s experience and ability. |
| 5 | Exceptional Response – A comprehensive and exceptionally well-evidenced submission that substantially exceeds the requirements and offers significant additional benefits. Submission clearly demonstrates exceptional expertise and knowledge, incorporating value-added benefits & other points of innovation. The bid is deemed to offer well-identified risks and a mitigation of these put forward and fully captures the understanding of the steps involved to deliver all the aspects of the service and is directly relatable to the question posed, giving an exceptionally high level of confidence in the Tenderer’s experience and ability. |

- The technical questions below are worth 80% of the total score. The individual question weightings are set out in the weighting column.

- The following formula will be applied for each question:

  - Points Scored ÷ Points Available × % weighting

  - The scores for each of the questions will be added to give a total Technical/Quality Score

- Unanswered questions or sections that are left blank shall be awarded a 0.

Please answer all questions in the spaces provided. Please do not attach documents or appendices.

| Question No. | Question | Weighting |
| --- | --- | --- |
| 1 | Specialist expertise Substantial experience designing and delivering judicial or legal-professional training on cybercrime, digital/electronic evidence, or related technology-law fields, ideally within Commonwealth or common-law jurisdictions. | 20% |
| Insert your answer here |  |  |
| 2 | Education Advanced degree in law, criminal justice or a closely related field (PhD will be an advantage) | 10% |
| Insert your answer here |  |  |
| 3 | Experience Minimum of ten (10) years of relevant experience supporting the strengthening of criminal justice systems, and/or proven research, policy, or teaching experience in critical areas of political, governance, social, human rights, or criminal law and training judicial officials. Familiarity with Nigeria's legal and institutional framework for cybercrime, or comparable experience in another African or Commonwealth common-law jurisdiction. | 25% |
| Insert your answer here |  |  |
| 4 | Practical skills Robust research design and content development skills, including the capacity to prepare accurate, relevant, reliable and analytical legal and policy documents. Excellent facilitation, communication and report-writing skills in English. Experience in judicial training or presenting to high-level audiences, including judicial officials. Experience in curriculum development will be an advantage | 25% |
| Insert your answer here. |  |  |

Part 4 – Pricing

Transparent pricing must be submitted with no hidden costs. Pricing and cost must be broken down to the different elements of the services and any other costs.

Please complete the Pricing Schedule and submit as a separate document. Please refer to Instructions to bidders which states that unless indicated otherwise, all prices should be quoted in Pounds Sterling.

The Consultant is expected (within their financial proposal) to provide a full breakdown of the number of experts/number of days (total and per expert) needed to complete the assignment.

Consultants are to give an indication as to which Band each Consultant’s fee falls within in the Secretariat’s Technical Assistance Consultants: Corporate Fee Band Table (see Annex 1). Include CVs of all staff proposed. Please note that the maximum daily fee rates can not normally exceed £700.

| For Consultancy: Consultant’s Name/Role/Band – refer to Annex 1 Technical Assistance Consultants: Corporate Fee Band Table Experts name/role |  | Day Rate (including all taxes) | No of Days | Total (including all taxes) GBP |
| --- | --- | --- | --- | --- |
| Total |  |  |  |  |

Payments will be made upon successful completion of the assignment, upon receipt of the Secretariat’s written approval of all agreed deliverables and upon submission of a compliant invoice. If there is a VAT element - for UK VAT registered consultant only – this must be itemised in the total quote received/agreed by the Secretariat and the consultant must submit a UK VAT registration certificate to the Secretariat when invoicing. All invoices will be sent to contract manager cybercrime@commonwealth.int

Annex 1 is to be included only for TAP Consultancy

Annex 1 – Secretariat’s Technical Assistance Consultants: Corporate Fee Band Table

The consultancy fee rate range associated with a particular level of assignment may be based on the following:

- Knowledge, qualifications, experience, and skills required.

- Level of work in terms of responsibilities and complexity of the assignment.

- Degree of specialisation required by the assignment.

| Band | Per Day (GBP) | Comments and Guidelines |
| --- | --- | --- |
| A* | 700+ | - Extensive achievement in their specialist field, in which they are nationally or internationally renowned. Extensive experience of leading or directing major, complex and business-critical projects, bringing genuine strategic insight, understanding the range of services to be delivered. In depth knowledge of the international sector/specialist field and of current policy and political issues affecting it. - Contributions to the accomplishment of a crucial programme or service or functional area of a broad scope, involving high complexity and impact. - Providing functional leadership and expert advice. - Preparing intricate and complex technical papers to working groups. - Undertaking the drafting of reports or proposals for projects of a large scale or a broad scope. - Large-scale programmatic and operational activities involving large commitments of staff and funds. - Rare specialization - Industry equivalent level: Partner/Managing Director |
| B | 500-699 | - Substantial experience in their specialist field and operating multiple major consultancy assignments achieving specific revenue and income objectives to agreed outcomes. - Within this category the person is expected to have significant, proven, industry recognised experience. - Expected to develop new approaches, techniques, or policies and/or design guidelines, standard operating procedures. - Providing technical support; leading group dynamics; and undertaking report drafting or project-wide proposals. - Industry equivalent level: Principal/Senior Consultant |
| C | 350 - 499 | - Demonstrable experience and relevant exposure in a range of projects in a specialist field. - Evidence of client facing experience and relationship management. - Support for planning and monitoring budgets and services to wider consultancy projects; and experience of proposal preparation. - Industry equivalent level: Consultant |
| D | 300-349 | - Specialized degree or training and - Several years of relevant experience - Industry equivalent level: Junior Consultant |
| E | £100 - £299 | - This level is established for the engagement of support services not available in the Secretariat related to projects or technical tasks of a narrow scope for which limited technical skills or experience are required. - Industry equivalent level: Project Support |

*Rates above Band A must include appropriate justification in respect of the tasks involved, complexity of the assignment, number of workdays involved, duration/period and specific task deliverables and must, internally within the Secretariat, be referred to the DSGs or Senior Director for review and approval ahead of any contract being awarded.

https://thecommonwealth.org/corporate-policies

https://thecommonwealth.org/corporate-policies

This will go some way to mitigate against bidders selecting the references that are likely to be more favorable and will assist in providing a more realistic reflection of performance.

Where contracts involve significant data processing, data protection cap needs to be determined on a case-by-case basis. For low-cost contracts that involve little (emails only) or no data processing, the liability is capped at 1.5 times of the contract value.